27th Green Belt Relay 17/18 May 2025

Green Belt Relay - Risk Assessment

v 0.11 May 2026

Purpose:

This document sets out the risks and mitigations identified by the organisers as a result of past successful events.

The first section is a summary of the overall risks and mitigations, as an introduction to the known risks of the event.

The second section is a detailed account of the entire course, with prioritised risks, and where a risk is more than “low”, a description of the mitigations.

This section focuses mainly on dangers from traffic, but also includes other external dangers such as other likely sports activities, livestock, etc.

It does not cover marking/navigation of the route, which is covered in a separate document, and it does not include arrangements for watering/feeding runners along the way – these are included in the marshalling and changeover plans.

Responsibilities

Mitigations here are ultimately the responsibility of the race director, Peter Kennedy.

Summary – Overall Risks

| Risk | Mitigation summary |
| --- | --- |
| Runners conflicting with road traffic on roads, road crossings and junctions, causing injury to themselves or accidents to the traffic (note that around 80% of the course is off-road) | - Marshalling plan covering all hazard points - Warning signs to alert motorists - Control system to verify that all critical marshalling points are covered, and to fill in or delay the race if they aren’t - See detailed risk assessment for step-by-step risk assessment of the full course |
| Runners encountering other people on the course e.g. pedestrians and bicycles on off-road sections, golf courses (stage 2, stage 13, 14, 18) or cricket games (stage 5, 7, 10) | - Hazards marked on runners’ maps where the path is especially narrow and/or likely to be crowded - Mandatory briefing before each stage to provide any updates - Provide written permission with relevant sports clubs prior to race |
| Runners clashing with horses on bridleways or livestock in fields | - Hazards marked on runners’ maps - Mandatory briefing before each stage to provide any updates - Re-routed stages to avoid danger points (esp. stage 6, 19 and 20) |
| Runners crossing railway level crossings (stage 3) | - Marshalling presence on any crossing, with clear segregation of duties to spot trains as well as guide runners |
| Route becoming impassable due to crop levels or vegetation | - Survey of likely trouble spots carried out before event (chiefly stage 11, but also 6), with re-routes possible |
| Medical emergencies (e.g. hot weather causing dehydration or sunstroke to runners) | - Dedicated paramedics provided in control car and sweep car - Regular watering points at marshal stops, and at stage finishes - Marshals to verify that all runners have completed the course - Runners mandated to carry a mobile phone with them |
| Runners get lost and are unable to reach the stage finish | - Runners must carry race maps, and are advised to carry a phone - Course marking plan in place to mark major turns |
| Members of the public remove or alter navigational markings prior to the race | - Runners must carry race maps, are advised to carry a phone, and can download GPS tracks of all routes - Markings have the date written on them, and a control for runners to see if they are the right way around - Regular marshal points on courses - Marshals (equipped with phone) to verify that all runners have completed the course |
| Traffic risks while transporting runners or organisers between stage starts/ends | - Provide guidance on routes between stages avoiding bottlenecks, and postcodes/grid references - Race director able to delay stages if traffic causes too many delays - Advise teams on website, race booklet, and captains’ briefing on the potential road hazards |
| Traffic risks to marshals while marshalling hazard points or changeover points | - High visibility clothing for marshals, with control car able to provide - Provide sufficient numbers of marshals to allow at least one person to watch traffic/hazards, rather than the race - Provide “caution runners” boards where there is a busy road near the changeover |
| Conflicting events making the safety measures impractical or causing additional hazards | - Mandatory briefing before each stage to provide any updates - Communication in place between marshals and timekeepers to provide warnings of any unexpected hazards and, if necessary, delay or stop the race |
| Financial commitments from organisers and teams | - Provide regular communication to teams on race organisation progress - Apply for all permissions and certifications early in the year - Maintain approx. 1 year revenue as surplus. |

Leg 1  -    Hampton Court   to   Staines     12.7 miles

| Course Identification |  | Green Belt Relay Stage 1 |  |  | A | B | C | D |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Whole event codes (1-8), (17, 29 & 31): 3, 4, 5, 7, 8, 17, 29, 31 |  |  |  |  | H/M/L | A to H | 9 to 30 only | R=Right, L=Left, SO=Straight On, FP=Footpath, FB=Footbridge |
| ID No | Miles from start |  | Details of hazard |  | Risk Rating level H/M/L | Persons at risk from hazard |  | Additional measures to reduce risk to LOW, with name of person or official function who will reduce the risk to low (if applicable) |
|  |  |  | Symbol | Desc. |  |  |  |  |
| 1. | 0.0 – 0.3 |  |  | Runners have to cross busy road on Hampton Court Bridge. Good visibility, pedestrian crossing | M | A, C, D, E, H, I | 11, 12, 16, 30 | 2 marshals lead the race and runners are obliged to follow them until towpath. 3 marshals at Pelican Crossing. Hazard marked on runners’ maps. CAUTION RUNNERS boards to warn traffic |
| 2. | 0.4 |  |  | Molesey boathouse - boats being carried across towpath to raft | L | A, H | 3 | Starters briefing to warn runners; hazard marked on runners’ maps |
| 3. | 0.3 – 5.0 |  |  | Runners run along towpath – bikes and pedestrians | L | A, H, I, J, K |  | n/a |
| 4. | 5.0 - 5.1 |  |  | Runners cross pedestrian bridge | L |  |  | n/a |
| 5. | 5.1 – 5.6 |  |  | Walton Lane. Runners run on LHS pavement | L | A, E |  | n/a |
| 6. | 5.6 |  |  | L onto Russell Road, run on LHS | L | A, B, C, E, J, K | 11, 23 | n/a |
| 7. | 5.6 – 6.0 |  |  | Russell Road, Halliford on Thames. Part paved, also traffic calming | L | A, E, I, J, K |  | n/a |
| 8. | 6.0 – 6.9 |  |  | Have to go on road for 10m at Old Shepperton Church Square (D, E). Good visibility | L | A, I, J | 23 | n/a |
| 9. | 6.9 – 7.7 |  |  | Pavement/ Road. This is the Thames Path – very quiet. Also, there is a path most of the way if runners choose | L | A, D, E, I, J, K | 23 | n/a |
| 10. | 7.7 – 8.65 |  |  | Thames Towpath to Chertsey Bridge | L | A, H, I J, K |  | n/a |
| 11. | 8.3 – 8.65 |  |  | Towpath / open field. Sometimes cattle in field, keep beside river and you should avoid them. | L | A, M | 23 | n/a |
| 12. | 8.65 |  |  | Under Chertsey Bridge. Water station. | L |  |  | n/a |
| 13. | 8.65 – 9.7 |  |  | Laleham Reach, narrow road (Thames Path) can be busy with day-trippers in Spring. Grass path on LHS. | L | A, B, D, E, I, H, J, K | 23 | n/a |
| 14. | 9.7 – 12.5 |  |  | Towpath | L | A, I, H, J, K |  | n/a |
| 15. | 12.5 – 12.7 |  |  | Staines Riverside Towpath. Footpath, narrow in places and possibly congested as along new Staines Riverside. | L | A, I, J, L | 23 | Mention in Starters Briefings. Hazard marked on runners’ maps. |

Green Belt Relay - Risk Assessment

Leg 2  -   Staines to Boveney – 9.42 miles

| Course Identification | Green Belt Relay Stage 2 |  |  | A | B | C | D |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Whole event codes (1-8), (17,29 & 31): 3, 4, 5, 7, 8, 17, 29, 31 |  |  |  | H/M/L | A to H | 9 to 30 only | R=Right, L=Left, SO=Straight On, FP=Footpath, FB=Footbridge |
| ID No | Miles from start | Details of hazard |  | Risk Rating level H/M/L | Persons at risk from hazard |  | Additional measures to reduce risk to LOW, with name of person or official function who will reduce the risk to low (if applicable) |
|  |  | Symbol | Desc. |  |  |  |  |
| 1 | 0.0 – 0.3 |  | Start – all on pavement and then towpath. | L | A, I, J | 11, 23 | n/a |
| 2. | 0.3 – 3.2 |  | Towpath | L | A, H, I, J, K | 11 | n/a |
| 3. | 3.2 – 3.3 |  | Pavement on RHS of A308 (Straight Road Windsor) | L | A, H, I, J, K | 11 | n/a |
| 4. | 3.3 – 5.0 |  | Thames Path from Old Windsor to Albert Bridge – in some parts uneven underfoot | L | A, H, I, J, K | 11 | n/a |
| 5. | 3.4 |  | Towpath / Sharp Drop into river - Left and Right around a dock mooring point | L | A, B, C, I, J | 11 | Hazard marked on runners’ maps |
| 6. | 5.0 – 5.1 |  | Up steps to road at Albert Bridge – Right over bridge on RHS pavement and then follow pavement into Datchet | L | A, B, C, E, J | 11 | n/a |
| 8. | 5.7 – 6.1 |  | On RHS pavement through Southlea Road, Datchet. | L | A, B, I J |  | n/a |
| 9. | 6.0 – 6.1 |  | Cross junction with The Avenue and then Queens Road | M | A, D, E, K | 11 | Course marking and marshal point. Hazard marked on runners’ maps |
| 11. | 7.3 |  | Road crossing – cross mini roundabout at entrance to Home Park | L | A, C, E | 11 | n/a |
| 12 | 7.4 |  | Road crossing – cross Farm Yard and then turn right into pedestrian area | L | A, C, E | 11 | Course marking and marshal point. Hazard marked on runners’ maps |
| 13 | 7.6 – 9.64 |  | Towpath | L |  |  | n/a |

Green Belt Relay - Risk Assessment

Leg 3 -  Boveney to   Little Marlow   11.2 miles

| Course Identification | Green Belt Relay Stage 3 |  |  | A | B | C | D |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Whole event codes (1-8),(17, 29 & 31): 3, 4, 5, 7, 8, 17, 29, 31 |  |  |  | H/M/L | A to H | 9 to 30 only | R=Right, L=Left, SO=Straight On, FP=Footpath, FB=Footbridge |
| ID No | Miles from start | Details of hazard |  | Risk Rating level H/M/L | Persons at risk from hazard |  | Additional measures to reduce risk to LOW, with name of person or official function who will reduce the risk to low (if applicable) |
|  |  |  | Desc |  |  |  |  |
| 11. | 0 – 4.2 |  | Thames Path to Maidenhead Bridge | L | A, H, I, J, K |  | n/a |
| 12. | 4.2 – 4.4 |  | Under Maidenhead Bridge and right then right again on footpath over river | L | A, C, D, E | 11 | n/a |
| 13. | 4.4 |  | Turn R onto A4094 pavement for 20 yards. Then back onto towpath. | L | A, C, D, E | 11 | n/a |
| 14. | 5.5 – 6.45 |  | Thames Path on pavement, next to A4094 to just after Boulters Lock | L | A, H, I, J, K |  | n/a |
| 15. | 5.5 |  | Veer R away from road and along Thames Path. | L | A, H, I, J, K | 23 | n/a |
| 16. | 6.9 – 7.4 |  | Thames Path turns L and away from river. | L | A, J | 23 | n/a |
| 17. | 7.4 - 7.7 |  | Mill Lane, Cookham. Narrow quiet road | L | A, D, E | 23 | n/a |
| 18. | 7.7 |  | Cross A4094 at Cookham. | H | A, C, D, E | 11, 23 | Marshals Hazard marked on runners’ maps CAUTION RUNNERS boards to warn traffic |
| 19. | 7.7- 7.8 |  | R on pavement Through Cookham Village | L | A, D, E | 23 | n/a |
| 20. | 7.8 |  | Road crossing - Past Cookham High Street to LHS. | M | A, C, D, E | 11 | Marshals Hazard marked on runners’ maps CAUTION RUNNERS boards to warn traffic |
| 21. | 7.8 – 8 |  | Through Cookham churchyard and L onto towpath | L | A, H, I J, K | 23 | n/a |
| 22. | 8.9 |  | Footbridge over Thames, on side of rail bridge. | L | A, I, J | 23 | n/a |
| 23. | 9.16 – 9.9 |  | Bourne End Riverside – crowded when weather is good. | L | A, H, I J, K |  | n/a |
| 24. | 9.9 |  | Turn right over level crossing and straight on along lane. Gates on either side. DANGER – Trains are really quiet, so you must look both L & R | H | A, M | 16 | Marshals, including one specifically to look for trains Hazard marked on runners’ maps Crossing has a fence either side, so runners have to stop before crossing |
| 25 | 10 – 11 |  | Lane / Road into the middle of Little Marlow then left to path | L | A, B, C, D, I | 23 | n/a |

Green Belt Relay - Risk Assessment

Leg 4  -    Lt. Marlow   to    Great Kingshill   12.2 miles

| Course Identification | Green Belt Relay Stage 4 |  |  | A | B | C | D |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Whole event codes (1-8),(17, 29 & 31): 3, 4, 5, 7, 8, 17, 29, 31 |  |  |  | H/M/L | A to H | 9 to 30 only | R=Right, L=Left, SO=Straight On, FP=Footpath, FB=Footbridge |
| ID No | Miles from start | Details of hazard |  | Risk Rating level H/M/L | Persons at risk from hazard |  | Additional measures to reduce risk to LOW, with name of person or official function who will reduce the risk to low (if applicable) |
|  |  | Symbol | Desc. |  |  |  |  |
| 1. | 0.0 – 0.25 |  | Narrow pavement. Start on pavement opposite athletics centre. Go east along pavement A4155 | L | A, B, C, D, E, J |  | n/a |
| 2. | 0.25 |  | Turn into Winchbottom Lane - narrow quiet road | L | A, D, E |  | n/a |
| 3. | 0.25 – 2.9 |  | Quiet narrow road – no pavement | L | A, D, E | 23 | n/a |
| 4. | 2.9 – 3.0 |  | Handy Cross. Turn R at T-junction. Cross over road, then over Ragmans Lane at Blacksmiths Arms and over stile into field. Good visibility | H | A, C, D, E | 11, 23 | Marshals Hazard marked on runners’ maps CAUTION RUNNERS boards to warn traffic |
| 5. | 3.0 – 4.5 |  | Fields and enclosed path | L | A, D, E | 23 | n/a |
| 7. | 4.5 – 4.55 |  | Turn R along Cressex Road | L | A, B, C, I | 11, 23 | n/a |
| 8. | 4.55 |  | Cross Cressex Road at mini roundabout and turn L into Gibson Road. Medium visibility. | M | A, C, D, E | 11, 23 | Marshals Hazard marked on runners’ maps CAUTION RUNNERS boards to warn traffic |
| 9. | 4.55 – 4.7 |  | Quite road with part pavement | L | A, D, E, I | 23 | n/a |
| 12. | 4.85 – 5.3 |  | Paths through Booker Common | L | A, J | 23, 28 | n/a |
| 13. | 5.3 |  | Cross straight over Lane End Road and onto wide path uphill. Runners run parallel to the road for a stretch so are aware it’s coming. Fast traffic. | H | A, B, C, D, E, K | 11, 23 | Marshals Hazard marked on runners’ maps CAUTION RUNNERS boards to warn traffic |
| 14. | 5.3 – 6.35 |  | Paths through High Barbers Wood | L | A, J | 23, 28 | n/a |
| 15. | 6.35 – 6.7 |  | Path / Bridleway – potential for horses on path | M | A, J, N | 4, 23, 28 | Pre-race briefing, and hazard marked on maps |
| 16. | 6.7 – 7.35 |  | Private & narrow road | L | A, D, E, K | 23 | n/a |
| 17. | 7.35 |  | Turn R onto A40 to West Wycombe, and cross road. Good visibility | H | A, B, C, D, E, | 11, 23 | Marshals Hazard marked on runners’ maps CAUTION RUNNERS boards to warn traffic |
| 18. | 7.35 – 7.9 |  | Road / pavement | L | A, B, C, D, E, I, J | 23 | SO thru West Wycombe Village |
| 19. | 7.9 |  | A40 / A4010 junction (roundabout). Cross over A4010 into Cookshall Lane. Good visibility | H | A, B, C, D, E, K | 11, 23 | Marshals Hazard marked on runners’ maps CAUTION RUNNERS boards to warn traffic |
| 20. | 7.9 – 8.1 |  | Cookshall Lane – narrow quiet road | L | A, D, E, K | 23 | n/a |
| 21. | 8.1 – 8.8 |  | Veer R onto enclosed bridleway | L | A, J | 23, 28 | n/a |
| 22. | 8.8 |  | Off path onto residential road. Turn L past entrance to Downley School and go SO on R of 2 adjacent paths. Marked on map. | L | A, I, J | 23, 28 | n/a |
| 23. | 8.8 – 8.9 |  | Enclosed path | L | A, J | 23, 28 | n/a |
| 24. | 8.9 – 9.0 |  | L into Plomer Green Lane, then R into Moor Lane – Quiet no-through roads, good visibility | L | A, C, D, E, I K | 11, 23 | Hazard marked on runners’ maps |
| 25. | 9.0 – 9.85 |  | Bridleway from Downley Common to Hughenden Manor | L | A, J, K | 23, 28 | n/a |
| 26. | 9.85 – 10.25 |  | Hughenden Manor Drive | L | A, D, E, I | 23 | n/a |
| 27. | 10.25 |  | Cattle Grid near exit to Manor grounds | L | A | 11, 23 | n/a |
| 28. | 10.25 – 11.0 |  | Exit Hughenden Manor and L on pavement along A4128 | L | A, J | 23 | n/a |
| 29. | 11.0 |  | Road crossing - Turn R just before roundabout to cross Valley Road and into Boss Lane. Good visibility | H | A, B, C, D, E, K | 11, 23 | Marshals Hazard marked on runners’ maps CAUTION RUNNERS boards to warn traffic |
| 30. | 11.0 – 11.3 |  | Boss Lane - Very quiet road | L | A, D, E, K | 23 | n/a |
| 31. | 11.3 – 11.8 |  | SO onto enclosed track uphill | L | A, J | 23, 28 | n/a |
| 32. | 11.8 – 12.0 |  | Past Pipers Corner School | L | A, D, E | 11, 23 | n/a |
| 33. | 12.0 – 12.1 |  | Turn L onto enclosed footpath | L | A, J | 23 | n/a |
| 34. | 12.1 – 12.2 |  | Turn R onto New Road | L | A, B, D, E, I | 11, 23 | n/a |
| 35. | 12.2 |  | Finish just before main road at Great Kingshill Village Hall | L | A, B, C, D, E, K | 11, 23 | n/a |

Green Belt Relay - Risk Assessment

Leg 5  -    Great Kingshill   to   Chipperfield   13.5 miles

| Course Identification | Green Belt Relay Stage 5 |  |  | A | B | C | D |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Whole event codes (1-8), (17, 29 & 31): 3, 4, 5, 7, 8, 17, 29, 31 |  |  |  | H/M/L | A to H | 9 to 30 only | R=Right, L=Left, SO=Straight On, FP=Footpath, FB=Footbridge |
| ID No | Miles from start | Details of hazard |  | Risk Rating level H/M/L | Persons at risk from hazard |  | Additional measures to reduce risk to LOW, with name of person or official function who will reduce the risk to low (if applicable) |
|  |  | Symbol | Desc |  |  |  |  |
| 1. | 0.0 – 0.1 |  | Start on Common Road, Gt Kingshill – Go south along road. Quiet residential | L | A, B, C, D, E, J | 11 | n/a |
| 2. | 0.1 – 0.2 |  | Turn L and onto path across field | L |  |  | n/a |
| 3. | 0.2 - 0.25 |  | Turn L along pavement – Cockpit Rd | L | A, I, J | 11 | n/a |
| 4. | 0.25 |  | Road crossing - Cross over crossroad at Cockpit Hole and Heath End Road and SO on LHS. Good visibility | M | A, C, D, E | 11, 23 | Marshals Hazard marked on runners’ maps CAUTION RUNNERS boards to warn traffic |
| 5. | 0.25 – 2.0 |  | Heath End Road / Windsor Lane to and thru’ Little Kingshill - Quiet roads. | L | A, D, E | 23 | n/a |
| 5a. | 2.0 |  | Turn R to cross Windsor Lane onto path signed South Bucks Way. Road crossing – good visibility | M | A, B, C, D , E | 11 | Marshals Hazard marked on runners’ maps CAUTION RUNNERS boards to warn traffic |
| 6. | 2.0 – 3.2 |  | South Bucks Way to Little Missenden | L | A, J | 23, 28 | n/a |
| 7. | 3.2 – 3.7 |  | L onto road from field and through Little Missenden. Poor visibility from hedges at first turn. | M | A, B, C, D, E, I | 11, 23 | Marshals Hazard marked on runners’ maps CAUTION RUNNERS boards to warn traffic |
| 8. | 3.3 |  | R in centre of village along Highmore Cottages and past Red Lion Pub | L | A, B, C, D, E | 11, 23 | n/a |
| 9. | 3.7 – 5.2 |  | Past Crown Inn and R onto South Bucks Way | L | A, J | 23, 28 | n/a |
| 10. | 5.2 |  | Narrow driveway - Exit from Shardeloes Estate / Amersham Cricket Club | L | A, C, J | 11, 23 | n/a |
| 11. | 5.2 – 5.6 |  | SO onto narrow path between trees | L | A, J | 23, 28 |  |
| 12. | 5.5 |  | Low bridge. Exit Shardoloes. Path goes beside river and under low bridge – taller runners may need to duck down | M | A, B, C, D, E, K | 11, 23 | Hazard marked on runners’ maps Pre-race briefing |
| 13. | 5.6 – 5.85 |  | Old Amersham High Street. Runners to stay on pavement and be careful of pedestrians | M | A, I, J | 23 | Hazard marked on runners’ maps |
| 14. | 5.85 |  | Road crossing, and turn L thru’ St Marys churchyard at Old Amersham. Good visibility, slow traffic | L | A, B, C, D, E, I, J | 11, 23 | Marshals Hazard marked on runners’ maps CAUTION RUNNERS boards to warn traffic |
| 15. | 5.85 – 6.0 |  | Path Thru’ churchyard | L | A, D, E, K | 23 | n/a |
| 16. | 6.0 – 6.5 |  | Path up past Martyrs Memorial | L | A, J | 23, 28 | n/a |
| 17. | 6.5 |  | Cross straight over A416 and SO onto public footpath. Path emerges suddenly onto road with no visibility. | H | A, B, C, D, E, I, J, K | 11, 23 | Marshals to form barrier Hazard marked on runners’ maps CAUTION RUNNERS boards to warn traffic |
| 18. | 6.5 – 6.9 |  | Footpath to Stanley Hill Avenue | L | A, J, K | 11, 23 | n/a |
| 19. | 6.9 – 7.1 |  | Quiet residential road | L | A, D, E, K | 23 | n/a |
| 20. | 7.1 – 7.2 |  | L along pavement – A404 | L | A, B, C, J | 11, 23 | n/a |
| 21. | 7.2 |  | Road crossing- L under railway into Woodside then R at mini-roundabout into Raans Road. Good visibility, traffic slowed for roundabout | M | A, B, C, D, E, I, J, K | 11, 23 | Marshals Hazard marked on runners’ maps CAUTION RUNNERS boards to warn traffic |
| 22. | 7.2 – 7.6 |  | Raans Road – use pavement on LHS | L | A, J | 23 | n/a |
| 23. | 7.6 |  | SO past Quill Hall Lane | L | A, J, K | 23 | n/a |
| 24. | 7.6 – 7.8 |  | Raans Road and past Raans Farm | L | A,J | 23 | n/a |
| 25. | 7.8 – 8.5 |  | Chiltern Forest – fork in path | L | A, J, K | 11, 23, 28 | n/a |
| 26. | 8.5 – 9.0 |  | Turn L onto Bell Lane - Quiet roads | M | A, J, K | 23, 28 | Hazard marked on runners’ maps |
| 27. | 8.75 |  | T-junction - Turn R along Latimer Road. | M | A, C, D, E | 11, 23 | Hazard marked on runners’ maps |
| 28. | 9.0 – 9.2 |  | Turn L thru’ KG and across field at Latimer Park Farm | L | A, J | 11, 23, 28 | n/a |
| 29. | 9.2 – 9.4 |  | Quiet private road | L | A, D | 23 | n/a |
| 30. | 9.4 |  | R at T-junction - Very minor junction | L | A, D, E, K | 23 | n/a |
| 31. | 9.4 – 9.65 |  | Road - Codmore Wood Road to Latimer | L | A, D, E, K | 23 | n/a |
| 32. | 9.65 |  | T-junction - Latimer Village. L after green onto Flaunden Hill | L | A, B, C, D, E, I, J, K | 23 | n/a |
| 33. | 9.65 – 11.35 |  | Road - Quiet narrow road, Flaunden Bottom | L | A, D, E, K | 23 | n/a |
| 34. | 11.35 |  | Crossroads - SO at crossroads at Flaunden, signed Belsize & Watford | M | A, B, D, E, K | 23 | Hazard marked on runners’ maps |
| 35. | 11.35 – 11.65 |  | Road - Quiet minor road | L | A, D, E | 11, 23 | n/a |
| 36. | 11.65 |  | T-junction - Cross minor road (Hog Pits) onto track / path thru’ wood | M | A, B, C, D, E, K | 11, 23 | Marshals Hazard marked on runners’ maps CAUTION RUNNERS boards to warn traffic |
| 37. | 11.65 – 12.2 |  | Path - Lower Plantation Wood | L | A, J | 23, 28 | n/a |
| 38. | 12.2 – 12.45 |  | Road - R onto Holly Hedges Lane -minor road | L | A, D, E | 23 | n/a |
| 39. | 12.45 – 12.8 |  | Path - Veer L thru’ Woodmans Wood on public footpath to Belsize | L | A, J | 23, 28 | n/a |
| 40. | 12.8 – 13.0 |  | Road - Over stile, cross minor road, then right at junction to Chipperfield | M | A, C, D, E, K | 11, 23 | Marshals Hazard marked on runners’ maps CAUTION RUNNERS boards to warn traffic |
| 41. | 13.0 – 13.5 |  | Road - Windmill Hill - Minor road | L | A, D, E, K |  | n/a |
| 42. | 13.5 |  | Road / green - Finish just before Chipperfield Green, next to Church | L | A, B, C, D, E, F, I, J | 11 | n/a |

Green Belt Relay - Risk Assessment

Leg 6  -    Chipperfield    to    St. Albans   8.5 miles

| Course Identification | Green Belt Relay Stage 6 |  |  | A | B | C | D |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Whole event codes (1-8),(17, 29 & 31): 3, 4, 5, 7, 8, 17, 29, 31 |  |  |  | H/M/L | A to H | 9 to 30 only | R=Right, L=Left, SO=Straight On, FP=Footpath, FB=Footbridge |
| ID No | Miles from start | Details of hazard |  | Risk Rating level H/M/L | Persons at risk from hazard |  | Additional measures to reduce risk to LOW, with name of person or official function who will reduce the risk to low (if applicable) |
|  |  | Symbol | Desc |  |  |  |  |
| 1. | 0.0 – 0.5 |  | Start along common | L | A, B, C, D, E, I, K | 11 | Marshal to warn traffic at 0.15 |
| 2. | 0.5 |  | Turn left and cross Common Road | H | A | 23, 28 | Marshals Hazard marked on runners’ maps CAUTION RUNNERS boards to warn traffic |
| 3. | 0.5 – 2.0 |  | Footpath | L | A, J | 23 | n/a |
| 7. | 2 |  | Residential road / path - L onto enclosed FP, SO across cul-du-sac (Archer Close) after 600m onto FP | L | A, D, E, I, J | 23 | n/a |
| 8. | 2.4 |  | Road crossing – cross high street. Busy road, but slow urban traffic, pedestrian crossing and good visibility | M | A, B, C, D, E, I, J, K | 11, 23 | 2 sets of marshals at Rose & Crown pub Kings Langley, Hazard marked on runners’ maps CAUTION RUNNERS boards to warn traffic |
| 9. | 2.4 - 3 |  | Footpaths and pavement to bridge over canal, then park | L | A, I, J | 23 | n/a |
| 12. | 3 |  | Road crossing - Cross over Primrose Hill onto signed FP. Urban traffic, good visibility | M | A, B, C, D, E, I, J, K | 11, 23 | Marshals Hazard marked on runners’ maps CAUTION RUNNERS boards to warn traffic |
| 13. | 3.0 – 3.2 |  | Path - Narrow path, beware of height restriction thru’ tunnel under railway. | L | A, J |  | n/a |
| 14. | 3.2 - 4 |  | Road - L down Oatlands then R at bottom onto Hart Hall Lane – minor roads | L | A, D, E, I, J, K | 23 | n/a |
| 16. | 4 – 4.7 |  | Footpath - Turn R, over stile and onto signed FP diagonally across fields | L | A, J | 23 | n/a |
| 18. | 4.7 |  | Road crossing - Cross Church Hill, Bedmond at Tin Church into Sergehill Lane. Busy road, but need to get over barrier to cross so hard to ignore | H | A, B, C, D, E, I, J, K | 11, 23 | Marshals Hazard marked on runners’ maps CAUTION RUNNERS boards to warn traffic |
| 19. | 4.7 – 7.1 |  | Road - Bedmond Lane – narrow quiet road | L | A, D, E, K | 23 | n/a |
| 20. | 6.1 |  | Crossroad - SO at crossroads - very minor, runners have right of way | L | A, D, E, K | 23 | n/a |
| 21. | 6.2 |  | Road to R - Bedmond Lane, minor road. L at Holy Bush Pub and under motorway. | L | A, B, D, E, K | 23 | n/a |
| 22. | 7.1 – 7.2 |  | Path - R off lane onto FP across field | L | A, J | 23 | n/a |
| 23 | 7.2 – 7.9 |  | Pavement / Path - Footpath through housing estate and up between houses, crossing some residential roads. | L | A, D, E, I, J, K | 23 | n/a |
| 24. | 7.9 |  | Road crossing. Crossroad at pelican crossing and straight on down “Verulamium Path to and past Roman Wall to LHS” Slow urban traffic (often congested) and good visibility | H | A, B, C, D, E, I, J, K | 11, 23 | Marshals Hazard marked on runners’ maps CAUTION RUNNERS boards to warn traffic |
| 25. | 7.9 – 8.4 |  | FP / Grass Path - Path thru Verulamium Park. | L | A, B, I, J, K | 23 | n/a |

Green Belt Relay - Risk Assessment

Leg 7  -    St. Albans    to   Letty Green        11.6 miles

| Course Identification |  | Green Belt Relay Stage 7 |  |  | A | B | C | D |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Whole event codes (1-8),(17, 29 & 31): 3, 4, 5, 7, 8, 17, 29, 31 |  |  |  |  | H/M/L | A to H | 9 to 30 only | R=Right, L=Left, SO=Straight On, FP=Footpath, FB=Footbridge |
| ID No | Miles from start |  | Details of hazard |  | Risk Rating level H/M/L | Persons at risk from hazard |  | Additional measures to reduce risk to LOW, with name of person or official function who will reduce the risk to low (if applicable) |
|  |  |  | Symbol | Desc |  |  |  |  |
| 1. | 0.0 – 0.65 |  |  | Towpath - Start on River Ver Path on east side of Holywell Hill. Narrow path | L | A, I, J | 23, 28 | Marshal to go ahead just before start and make pedestrians aware that run is just about pass. |
| 2. | 0.3 |  |  | Road crossing - Cross Cotton Mill Land & back onto Ver Path. Limited visibility | M | A, D, E, I, J, K | 11, 23 | Starters Briefing Marshals CAUTION RUNNERS boards Hazard marked on map. |
| 3. | 0.6 |  |  | Steps - R up steps before over head bridge. | L | A, J | 23 | n/a |
| 4. | 0.6 – 0.9 |  |  | Path / Cycle track - L along Alban Way cycle path | L | A, I, J, K | 23 | n/a |
| 5. | 0.9 – 1.0 |  |  | Pavement - SO on pavement thru’ new housing estate staying on RHS pavement | L | A, D, E, I, J, K | 23 | n/a |
| 6. | 1.0 – 4.8 |  |  | Path /Cycle Track - Alban Way | L | A, J, K | 23 | n/a |
| 7. | 1.9 |  |  | Road crossing – cross Sutton Rd and continue on Alban Way. Minor road, good visibility | M | A, D, E, I, J, K | 11, 23 | Starters Briefing Marshals CAUTION RUNNERS boards Hazard marked on map. |
| 8. | 4.9 - 5.0 |  |  | Pavement - Up to Galleria and turn R on pavement / bridge over Motorway | L | A, D, E, I, J, K | 23 | n/a |
| 9. | 5.0 – 6.35 |  |  | Path / Cycle track - Turn R to Subway under road - the Alban Way path | L | A, J, K | 23 | n/a |
| 10. | 5.25 |  |  | Road crossing - Cross straight over St Albans Road West minor road and onto Alban Way. Good visibility | M | A, D, E, I, J, K | 23, 10 | Marshals CAUTION RUNNERS boards Hazard marked on map. |
| 11. | 5.4 |  |  | Road Crossing - Cross Lemsford Road and back onto Alban Way. | M | A, D, E, I, J, K | 23, 10 | Marshals CAUTION RUNNERS boards Hazard marked on map. |
| 12. | 6.0 |  |  | Cross Road - Cross SO Ground Lane and back onto Alban Way – residential road. | M | A, C, D, E, I, J, K | 11, 23 | Marshals CAUTION RUNNERS boards Hazard marked on map. |
| 13. | 6.0 – 6.35 |  |  | Path / Cycle track - Alban Way | L | A, I, J | 23 | n/a |
| 14. | 6.35 – 6.4 |  |  | Footbridge over rail - SO over footbridge then turn L and back onto path | L | A, J | 23 | n/a |
| 15. | 6.4 – 6.55 |  |  | Pavement / Road - Turn R onto pavement, crossing residential road when safe (The Ryde) | L | A, J | 23 | n/a |
| 16. | 6.55 – 7.0 |  |  | Pavement / Cycle Track - Turn L into Park View. Residential road then descends on cycle path to main road A1000. Stay on LHS. | L | A, J | 23 | n/a |
| 17. | 6.95 |  |  | Road crossing - Minor residential road to LHS (Lodge Drive) | M/L | A, B, C, D, E, J, K | 23, 11 | Hazard marked on map |
| 18. | 7.0 |  |  | Road crossing - Just after Lodge Drive turn R to cross A1000 using traffic island, then turn L on pavement over bridge over A414 | H | A, B, C, D, E, J, K | 23, 11 | Marshals CAUTION RUNNERS boards Hazard marked on map. |
| 19. | 7.0 – 7.1 |  |  | Pavement - Along A1000 cross bridge over A414 | L | A, D, E, K | 23 | n/a |
| 20. | 7.1 – 7.25 |  |  | Path / Road - Turn R and down path and very quiet road past Mill Green Mill | L | A, B, D, E, I, J, K | 23 |  |
| 21. | 7.25 |  |  | Road crossing - Cross minor road and straight on between bollards onto path/cycle track | L | A, B, C, D, E, I, J, K | 11, 23 | n/a |
| 22. | 7.25 – 7.8 |  |  | Path/ Cycle Track - SO along pavement / cycle track parallel to A414 | L | A, I, K | 23 | n/a |
| 23. | 7.8 – 8.15 |  |  | Road - Turn L along Gypsy Lane. Minor road past golf club | L | A, D, E, K, P | 23 | n/a |
| 24. | 8.15 – 8.25 |  |  | Path on golf course - Turn R along path along edge of golf course and with Cricket Club to LHS | L | A, I, J, P | 23 | n/a |
| 27. | 8.25 – 9.25 |  |  | Path thru woods - Into woods and turn R to follow paths through Commons Woods. Can be uneven underfoot | L | A, I, J, P | 23 | n/a |
| 28. | 9.25 – 9.6 |  |  | Path - Grassy path around 3 sides of field | L | A, I, J | 23 | n/a |
| 29. | 9.6 |  |  | Footbridge - Could be slippery if wet | L | A, I, J | 23 | n/a |
| 30. | 9.6 – 9.8 |  |  | Path - Crosses wooden elevated path and footbridge. | L | A, I, J | 23 | n/a |
| 31. | 9.8 – 9.9 |  |  | Path - Turn R along RH edge of common | L | A, I, J | 23 | n/a |
| 32. | 9.9 – 10.0 |  |  | Path - Turn R on FP between houses. Crosses 2 residential roads | L/M | A, E, I, J | 23 | n/a |
| 33. | 10.0 – 10.25 |  |  | Lane - Turn L after garages along Holwell Hyde Lane. Very quiet lane | L | A, E, I, J | 23 | n/a |
| 34 | 10.25 – 10.35 |  |  | Road - Turn R at end of lane on grass verge – Cole Green Lane | L | A, C, D | 11, 23 | n/a |
| 35 | 10.35 – 12.0 |  |  | Path / Cycle track - Turn R onto Cole Green Way. Follow to finish at Old Cole Green Station | L | A, I, J, K | 23 | n/a |

Green Belt Relay - Risk Assessment

Leg 8  -    Letty Green    to    Dobbs Weir       10.65 miles

| Course Identification | Green Belt Relay Stage 8 |  |  | A | B | C | D |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Whole event codes (1-8),(17, 29 & 31): 3, 4, 5, 7, 8, 17, 29, 31 |  |  |  | H/M/L | A to H | 9 to 30 only | R=Right, L=Left, SO=Straight On, FP=Footpath, FB=Footbridge |
| ID No | Miles from start | Details of hazard |  | Risk Rating level H/M/L | Persons at risk from hazard |  | Additional measures to reduce risk to LOW, with name of person or official function who will reduce the risk to low (if applicable) |
|  |  | Symbol | Desc |  |  |  |  |
| 1. | 0.0 – 2.1 |  | Path / Cycle track - Starts at on Cole Green Way at Old Cole Green Station, Letty Green. SO along Cole Green Way | L | A, I, J, K | 23 | n/a |
| 3. | 2.1 – 2.4 |  | Track / Lane to Football Club - Turn R 50m before railway viaduct for just a few yards then L on enclosed wide track and after 250m thru car park of Hertford Football Club and SO along lane. | L | A, D, I, J, K | 23 | n/a |
| 4. | 2.4 |  | Pavement / Road - Turn L along road. Horns Lane then West Street, Hertford. Stay on LHS pavement then cross over to RHS when safe. | L | A, D, E, I,J, K | 23 | n/a |
| 5. | 2.4 – 2.7 |  | Pavement / Road - West Street, Hertford | L | A, D, E, I , J, K | 23 | n/a |
| 6. | 2.7 – 2.75 |  | Pavement - At end of West Street turn R staying on RHS pavement with dual carriageway to LHS – Gascoyne Way | L | A, B, C, I, K | 23 | n/a |
| 7. | 2.75 – 2.8 |  | Subway - Veer R / SO and down to subway to turn L thru subway. | L | A, I, J, K | 23, 11 | n/a |
| 8. | 2.8 |  | Road crossing - Cross Stile Street (very quiet) and SO into Castle grounds. | L | A, D, E, I, J, K |  | n/a |
| 9. | 2.8 – 3.0 |  | Path / Car Park - Cross Stile Street (very quiet) and SO into Castle grounds. Path soon goes L and climbs to castle wall. At top turn R thru gate and past castle to your LHS. Stay SO, then after 60m turn L with path keeping wall to your RHS. After another 60m turn R thru gate and SO thru car park of Castle Hall | L | A, B, C, D, E, I, J, K | 23 | n/a |
| 10. | 3.0 |  | Road crossing - Cross road at pelican crossing and straight on into Maidenhead Street. | M | A, D, E, I, J, K | 11, 23 | Marshals CAUTION RUNNERS boards Hazard marked on map. |
| 11. | 3.0 – 3.1 |  | MARKET / pedestrian street - Maidenhead Street – Saturday Market – Lots of people about. Runners to stay on LHS | L | A, B, C, I , J, K, R | 11, 23 | Marshals |
| 12. | 3.1 – 3.15 |  | Pavement / Road - At end of Maidenhead Street turn L into Bull Plain staying on LHS pavement and over bridge | L | A, D, E, I, J, K | 23 | n/a |
| 13. | 3.15 – 3.2 |  | Road / Pavement - Over canal then R along road. Cross over to RHS a.s.a.p and stay R of Barge Pub onto path along canal | L | A, D, E, I, J, K | 23 | n/a |
| 14. | 3.2 – 3.5 |  | Towpath - Along River Lea Navigation | L | A, H, I, J, K | 23 | n/a |
| 15. | 3.5 |  | Footbridge / Road crossing - SO over FB and up to road / lane (Mill Lane, Hertford). Turn R over canal then L to cross narrow lane and back onto towpath | L | A, D, E, I, J, K | 23, 11 | n/a |
| 16 | 3.6 – 5.7 |  | Towpath - River Lee Path | L | A, H, I, J, K | 23 | n/a |
| 18. | 5.7 |  | Road crossing. River Lea path crosses Amwell End at Ware – busy road, good visibility | H | A, B, C, E, I, J, K | 11, 23 | Marshals CAUTION RUNNERS boards Hazard marked on map. |
| 19. | 5.7 – 10.65 |  | Towpath - River Lee Path | L | A, H, I, J, K | 23 | n/a |
| 20. | 7.6 |  | Lock - Thru gates at Stanstead Lock | L | A, H, I, J, K | 23 | n/a |
| 21. | 7.75 |  | Towpath under bridge - Stay L on towpath under bridge at Station Road, St Margarets | L | A, H, I, J, K | 23 | n/a |
| 22. | 9.1 |  | Towpath under bridge - Stay L on towpath under bridge at Rye Road | L | A, H, I, J, K | 23 | n/a |
| 23. | 9.8 |  | Lock - Past Fieldes Weir Lock | L | A, H, I, J, K | 23 | n/a |
| 24. | 10.6 |  | Footbridge over weir - Turn L over footbridge to finish on grassy picnic area at Dobbs Weir | L | A, H, I, J, K | 23 | n/a |

Green Belt Relay - Risk Assessment

Leg 9  -     Dobbs Weir    to    High Beach     10.2 miles

| Course Identification | Green Belt Relay Stage 9 |  |  | A | B | C | D |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Whole event codes (1-8),(17, 29 & 31): 3, 4, 5, 7, 8, 17, 29, 31 |  |  |  | H/M/L | A to H | 9 to 30 only | R=Right, L=Left, SO=Straight On, FP=Footpath, FB=Footbridge |
| ID No | Miles from start | Details of hazard |  | Risk Rating level H/M/L | Persons at risk from hazard |  | Additional measures to reduce risk to LOW, with name of person or official function who will reduce the risk to low (if applicable) |
|  |  | Symbol | Desc |  |  |  |  |
| 1. | 0.0 |  | Towpath - Starts on River Lee Path, Dobbs Weir, just south of Dobbs Weir Road and next to public car park. | L | A, H, I, J, K |  | n/a |
| 2. | 0.0 – 1.5 |  | Towpath. River Lee Path. Path may be uneven underfoot | L | A, H, I, J, K | 23 | n/a |
| 3. | 0.2 |  | Towpath - Past Dobbs Weir Lock | L | A, H, I, J, K | 23 | n/a |
| 4. | 0.9 |  | Towpath - Past Carthagena Lock | L | A, H, I, J, K | 23 | n/a |
| 5. | 1.5 |  | Road crossing - Towpath comes up to Old Nazeing Road (next to Crown Pub). Turn R over bridge (narrow road), then L and back onto towpath. Good visibility, slow traffic | M | A, B, C, D, E, I, J, K | 11, 23 | Hazard marked on runners’ maps. |
| 6. | 1.5 – 7.05 |  | Towpath - River Lee Path | L | A, H, I, J, K |  | n/a |
| 7. | 2.95 |  | Towpath - Aqueduct Lock | L | A, H, I, J, K |  | n/a |
| 8. | 3.85 |  | Towpath - Cheshunt Lock | L | A, H, I, J, K |  | n/a |
| 9. | 4.6 |  | Towpath - Waltham Common Lock | L | A, H, I, J, K |  | n/a |
| 10. | 5.5 |  | Towpath - Waltham Town Lock | L | A, H, I, J, K |  | n/a |
| 11. | 5.55 |  | Low Bridge overhead - River Lee Path passes under Station Road, Waltham Abbey. Be careful not to bang head | L | A, H, I, J, K | 23 | n/a |
| 12. | 6.1 |  | Towpath - Rammey Marsh Lock | L | A, H, I, J, K |  | n/a |
| 13. | 7.0 |  | Road crossing / road - Enfield Lock – Turn L on road then R into Swan and Pike Road and past Rifles Pub (now closed) to your LHS. We have now left the River Lee Path | M | A, B, C, D, E, I, J, K | 11 | Hazard marked on runners’ maps. |
| 14. | 7.05 – 7.85 |  | Towpath / path - L onto towpath, signed London Loop. Follow London Loop signs over 3 footbridges and thru park / marsh | L | A, I, J, K | 23 | n/a |
| 15. | 7.85 – 7.9 |  | Pavement - Exit Stewardstone Marsh / Lee Valley Park onto Godwin Close. Stay on LHS pavement. | L | A, I, J, K | 23 | n/a |
| 16. | 7.9 – 8.1 |  | Pavement - Turn L along A112 staying on LHS pavement. | L | A, I, J, K | 23 | n/a |
| 17. | 8.1 |  | Road Crossing - Turn R to cross A112, at Plough Pub and down Mott Street. Busy road, good visibility | H | A, B, C, D, E, I, J, K | 11, 23 | Marshals CAUTION RUNNERS boards Hazard marked on map. |
| 18. | 8.1 – 10.2 |  | Road - Mott Street, quiet road thru’ Epping Forest | L | A, B, C, D, E, I, J, K, M | 23 | n/a |
| 19. | 8.9 |  | Road junction - Past Lippitts Hill to RHS – minor road | L | A, B, C, D, E, I, J, K, M | 23 | n/a |
| 20. | 9.65 |  | Road junction - Past Church Road to RHS – minor road | L | A, B, C, D, E, I, J, K, M | 23 | n/a |
| 21. | 9.75 |  | Road crossing - SO over Avey Lane - Minor crossroads | M | A, B, C, D, E, I, J, K, M | 11, 23 | Hazard marked on maps |
| 22. | 10.05 |  | Road junction - Past Wellington Hill to LHS – minor road | L | A, B, C, D, E, I, J, K, M | 23 | n/a |
| 23. | 10.1 |  | Car park - High Beach, maybe very busy | L | A, B, C, D, E, I, J, K, N | 11, 23 | n/a |
| 24. | 10.1 – 10.2 |  | Path - Veer slightly R onto and diagonally Across High Beach Green to finish at large Oak Tree on Green just opposite entrance to Epping Forest Field Centre. On hot days the green can be busy with day-trippers, so marshals should ensure clear route across green for runners. | L | A,B, C, I, J, K, N | 23, 28 | n/a |

Green Belt Relay - Risk Assessment

Leg 10  -     High Beach    to    Toot Hill     9 miles

| Course Identification | Green Belt Relay Stage 10 |  |  | A | B | C | D |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Whole event codes (1-8),(17, 29 & 31): 3, 4, 5, 7, 8, 17, 29, 31 |  |  |  | H/M/L | A to H | 9 to 30 only | R=Right, L=Left, SO=Straight On, FP=Footpath, FB=Footbridge |
| ID No | Miles from start | Details of hazard |  | Risk Rating level H/M/L | Persons at risk from hazard |  | Additional measures to reduce risk to LOW, with name of person or official function who will reduce the risk to low (if applicable) |
| 1. | 0.0 – 1.25 |  | Path / Bridleway - Start on FP next to Corporation of London sign on north side of entrance road to High Beach Field Centre. Follow path north. | L | A, I, J, K, N | 23 | n/a |
| 2. | 1.25 |  | Road crossing - Cross straight over A121 and onto wide bridleway | H | A, B, C, D, E, I, J, K, N | 11, 23 | Marshals, checked by control car CAUTION RUNNERS boards Hazard marked on map. |
| 3. | 1.25 – 2.2 |  | Path / bridleway - Footpaths / bridleways thru Epping Forest | L | A, I, J, K, N | 23 | n/a |
| 5. | 2.2 |  | Road crossing - Cross straight over Crown Hill – quiet road, good visibility | M | A, B, C, D, E, I, J, K, N | 11, 23 | Marshals, checked by control car CAUTION RUNNERS boards Hazard marked on map. |
| 6. | 2.2 – 3.1 |  | Bridleway | L | A, I, J, K, N | 23 | n/a |
| 7. | 3.1 – 3.5 |  | Run on pavement along busy road | L | A, B, C, D, E, I, J, K, N | 11, 23 | n/a |
| 13. | 3.5 |  | Road crossing - Turn R to cross Theydon and onto Bell Common. Use traffic islands | H | A, B, C, D, E, I, J, K | 11, 23 | Marshals, checked by control car CAUTION RUNNERS boards Hazard marked on map. |
| 14. | 4.2 – 4.55 |  | Lane - Bell Common – residential cul-du-sac | L | A, D, E, I, J, K | 23 | n/a |
| 15. | 4.55 – 4.75 |  | Path thru Common - At end of road go SO onto grass. Veer half R over road then turn R on grass path downhill. At gap in trees, turn L onto enclosed path between trees. | L | A, I, J, K | 23 | n/a |
| 16. | 4.75 – 5.0 |  | Pavement - Turn L along pavement - Western Ave | L | A, B, C, J, K | 23 | n/a |
| 17. | 5.0 |  | Road crossing - Turn R and cross over Central Drive onto signed FP between houses. Good visibility. | M | A, B, C, D, E, I, J, K | 11, 23 | Hazard marked on map |
| 18. | 5.0 – 5.15 |  | Path - FP to Epping Station | L | A, B, C, I, J, K | 11, 23 | n/a |
| 19. | 5.15 |  | Car park - Epping Station car park | L | A, C, E, I, K |  | n/a |
| 20. | 5.15 |  | Road crossing - SO over road to Epping Station car park and up steps and over footbridge | H | A, B, C, D, E, I, J, K | 11, 23 | Marshals, checked by control car CAUTION RUNNERS boards Hazard marked on map. |
| 21. | 5.15 – 5.3 |  | Footbridge / path - Epping Station. Off footbridge and L along Hill Crescent Way | L | A, B, C, E, I, J, K | 11, 23 | n/a |
| 22. | 5.3 |  | Road crossing - Turn R at T-junction staying on RHS pavement. Cross over to LHS asap. | M | A, B, C, D, E, I, J, K | 11, 23 | Marshals Hazard marked on runners’ maps CAUTION RUNNERS boards to warn traffic |
| 23. | 5.25 – 5.3 |  | Pavement - Bower Hill, Epping | L | A, I, J, K | 23 | n/a |
| 24. | 5.3 – 5.8 |  | Path - Turn L onto enclosed FP, sign Essex Way & soon downhill on LHS of field | L | A, I, J, K | 23 | n/a |
| 25. | 5.8 |  | Road - L onto road, then L between houses | L | A, D, E, I, J, K | 23 | n/a |
| 26. | 5.8 – 6.4 |  | Track - Green Lane – ancient track | L | A, I, J, K, N | 23 | n/a |
| 27. | 6.4 |  | Road crossing - Coopersale Street. Turn R along road then L to cross and into Houblons Hill. BEWARE of ditch on green. | H | A, B, C, D, E, I, J, K | 11, 23 | Marshals, checked by control car CAUTION RUNNERS boards Hazard marked on map. |
| 28. | 6.4 – 7.0 |  | Road - Houblons Hill – Run on LHS | L | A, D, E, I, J, K | 23 | n/a |
| 29. | 7.0 |  | Road crossing - Cross road just past Church and through small school car park | M | A, D, E, I, J, K | 23, 11 | Marshals Hazard marked on runners’ maps CAUTION RUNNERS boards to warn traffic |
| 30. | 7.0 – 9.4 |  | Path - SO on FP - Essex Way | L | A, I, J, K, N | 23 | n/a |
| 31. | 7.3 |  | Path - At T-junction of FPs turn R and soon downhill to cross footbridge over M11 | L | A, I, J, K, N | 23 | n/a |
| 32. | 7.7 |  | Path - As main track / lane turns R, go SO onto footpath – Essex Way | L | A, I, J, K, N | 23 | n/a |
| 33. | 9.2 |  | Path - As Essex Way turns R and thru hedgerow, stay SO and soon L and towards water tower in distance | L | A, I, J, K, N | 23 | n/a |
| 34. | 9.4 – 9.7 |  | Lane - Immediately before water tower, turn R past fast farmhouse and along lane | L | A, B, C, D, E, I, J, K, N | 23 | n/a |
| 35. | 9.7 |  | Finish - Finish near end of Mill Lane at Toothill and just before T-junction | L | A, B, C, D, E, I, J, K, N | 11, 23 | n/a |

Green Belt Relay - Risk Assessment

Leg 11  -      Toot Hill    to    Blackmore         7.5 miles

| Course Identification | Green Belt Relay Stage 11 |  |  | A | B | C | D |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Whole event codes (1-8),(17, 29 & 31): 3, 4, 5, 7, 8, 17, 29, 31 |  |  |  | H/M/L | A to H | 9 to 30 only | R=Right, L=Left, SO=Straight On, FP=Footpath, FB=Footbridge |
| ID No | Miles from start | Details of hazard |  | Risk Rating level H/M/L | Persons at risk from hazard |  | Additional measures to reduce risk to LOW, with name of person or official function who will reduce the risk to low (if applicable) |
|  |  | Symbol | Desc |  |  |  |  |
| 1. | 0.0 |  | Start - Start in Mill Lane, just before junction with Toot Hill Road. Good visibility | L | A, B, C, D, E, I, J, K, N | 11, 23 | n/a |
| 2. | 0.0 – 0.8 |  | Road - Turn L into Toot Hill Road, run on LHS. Good visibility | L | A, B, C, D, E, I, J, K, N | 23 | n/a |
| 3. | 0.8 |  | T-Junction - Turn R at T-junction onto Toot Hil Common – run on RHS. Good visibility and plenty of time to cross | M | A, D, E, I, J, K, N | 23 | Hazard marked on map |
| 4. | 0.8 - 1.25 |  | Road - Toot Hill Common | L | A, B, C, D, E, I, J, K | 23 | n/a |
| 5. | 1.25 – 1.8 |  | Path - Immediately past entrance to Greensted Farm, turn L onto FP signed Essex Way, then SO along LHS of fields | L | A, I, J, K | 23, 28 | n/a |
| 6. | 1.8 |  | Footbridge / T-junction - Out of field over FB then R along lane / track | L | A, D, E, I, J, K | 23 | n/a |
| 7. | 1.8 – 1.95 |  | Lane - Lane to Greensted – on reaching houses stay L thru gate signed FP | L | A, D, E, I, J, K | 23, 28 | n/a |
| 8. | 1.95 |  | Lane / Path - Immediately after church turn L onto Lane / FP, signed Essex Way | L | A, I, J, K | 23, 28 | n/a |
| 9. | 1.95 – 2.75 |  | Path across fields to Chipping Ongar | L | A, I, J, K | 23, 28 | n/a |
| 10. | 2.2 |  | Cross Lane - Cross straight over narrow lane | L | A, E, I, J, K | 23 | n/a |
| 11. | 2.75- 2.85 |  | Road - Over concrete bridge and SO on lane past Sainsbury’s – Stay on RHS | L | A, B, C, D, E, I, J, K | 23 | n/a |
| 12. | 2.85 |  | Road Crossing - At T-junction turn R on pavement then L to Cross Chipping Ongar High Street using Zebra Crossing | M | A, B, C, D, E, I, J, K | 11, 23 | Slow high street traffic and zebra crossing Hazard marked on map |
| 13. | 2.85 – 3.0 |  | Busy pavement - Turn R on pavement along Chipping Ongar High Street | L/M | A, B, C, D, E, I, J, K | 11, 23 | n/a |
| 14. | 3.0 – 3.2 |  | Road - Turn L into Castle Street. Quiet cul de sac | L | A, B, C, D, E, I, J, K | 23 | n/a |
| 15. | 3.2 – 4.0 |  | Path / (Essex Way) - At lamp-post marked Spring Meadow go thru kissing-gate on LHS and stay L on FP. Follow FP after 0.2 miles as it turns R past playground then L | L | A, I, J, K | 23, 28 | n/a |
| 16. | 3.6 |  | Path - On entering field, immediately turn R and on FP along RHS of field | L | A, I, J, K | 23, 28 | n/a |
| 17. | 3.75 |  | Path - Thru wide opening into field and SO towards metal FB in distance (now leave Essex Way as it turns L) | L | A, I, J, K | 23, 28 | n/a |
| 18. | 3.8 |  | Footbridge - Over metal footbridge and SO | L | A, I, J, K | 23, 28 | n/a |
| 19. | 4.0 – 4.2 |  | Path / Pavement- Up steps, then L across grass, soon on pavement then behind houses. | L | A, B, C, D, E, I, J, K | 23, 28 | n/a |
| 20. | 4.2 |  | Road crossing - Turn R along pavement (Mill Lane, High Ongar), after 50m turn L to cross road and onto FP signed Essex Way. Good visibility and plenty of time to cross | M | A, B, C, D, E, I, J, K | 11, 23 | Hazard marked on map Marshals (check crop levels in fields prior to race) |
| 21. | 4.2 – 4.5 |  | Path in field - On entering field take FP half R across field, signed FP & St Peters Way | L | A, I, J, K | 23, 28 | n/a |
| 22. | 4.5 – 5.25 |  | Lane - Out of field and L onto Lane to farm. | L | A, D, E, I, J, K, N | 23, 28 | n/a |
| 23. | 5.25 – 5.35 |  | Farm - SO past Paslow Hall Farm to RHS | L | A, D, E, I, J, K, M, N | 23, 28 | n/a |
| 24. | 5..35 – 6.3 |  | Path - After pond to LHS turn R on wide track | L | A, I, J, K, N | 23, 28 | n/a |
| 25. | 6.3 |  | Road Crossing - Cross Nine Ashes Road to Paslow Common Farm. Good visibility. | M | A, B, C, D, E, I, J, K, N | 11, 23 | Hazard marked on map Marshals |
| 26. | 6.3 – 6.45 |  | Farm - SO to Paslow Common Farm, stay R past farm buildings, then L behind them. At end of buildings turn R on path towards church spire in distance. | L | A, D, E, I, J, K, M, N | 23, 28 | n/a (check crop levels in fields prior to race) |
| 27. | 6.45 – 7.4 |  | Path / ditch - Path crosses field then runs parallel to ditch to LHS of path. | L | A, I, J, K, N | 23, 28 | n/a |
| 28. | 7.1 – 7.15 |  | Lane / T-junction - SO along lane. At T-junction turn L along pavement staying on LHS | L | A, B, C, D, E, I, J, K | 23, 28 | n/a |
| 29. | 7.4 |  | Road crossing - Turn R to cross Blackmore Rd onto FP across field. Village road with good visibility and plenty of time to cross | M | A, B, C, D, E, I, J, K | 11, 23, 28 | Hazard marked on map Marshals |
| 31. | 7.4 – 7.5 |  | Path - At y-junction of FPs turn L then after 50m turn R towards finish | L | A, I, J, K | 23, 28 | n/a |

Green Belt Relay - Risk Assessment

Leg 12 - Blackmore to Thorndon Park North Countryside Centre 10.75 m

| Course Identification | Green Belt Relay Stage 12 |  |  | A | B | C | D |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Whole event codes (1-8),(17, 29 & 31): 3, 4, 5, 7, 8, 17, 29, 31 |  |  |  | H/M/L | A to H | 9 to 30 only | R=Right, L=Left, SO=Straight On, FP=Footpath, FB=Footbridge |
| ID No | Miles from start | Details of hazard |  | Risk Rating level H/M/L | Persons at risk from hazard |  | Additional measures to reduce risk to LOW, with name of person or official function who will reduce the risk to low (if applicable) |
|  |  | Symbol | Desc |  |  |  |  |
| 1. | 0.0 – 0.1 |  | Road - Start in Church Street just opposite small green. Turn R along The Green | L | A, B, C, D, E, I, J, K | 11, 23 | n/a |
| 2. | 0.1 |  | Road junction - Turn R at T-junction into Ingatestone Road. Quiet roads | L | A, D, E, J, K | 11, 23 | n/a |
| 3. | 0.1 – 3.6 |  | Road | L | A, D, E, J, K | 23 | n/a |
| 4. | 0.9 |  | Junction - Road veers left, two minor roads from right. Runner’s road has right of way. | L | A, D, E, J, K | 23 | n/a |
| 5. | 1.8 |  | Road - SO past Blackmore Road to LHS. Runner’s road have right of way. | L | A, C, D, E, K | 23 | n/a |
| 6. | 3.6 |  | Pavement - Turn R onto pavement at T-junction Trueloves Lane / B1002. Stay on pavement on RHS | L | A, C, D, E, J | 23 | n/a |
| 7. | 3.6 – 4.35 |  | Pavement - Runners may choose to cross over before 4.35 miles – if so, do with care. | L | A, I, J | 23 | n/a |
| 8. | 4.35 |  | Turn L into Church Road, signed Billericay | M | A, D, E, I, J, K | 11, 23 | Marshals Hazard marked on map |
| 9. | 4.35 – 4.7 |  | Pavement / Road - Church Road Run on pavement on LHS. Small, quiet road. | L | A, D, E, J, K | 23 |  |
| 10. | 4.55 |  | Road - Road narrows with no pavement on bridge over railway – run on LHS | M | A, D, E, J, K | 23 | Hazard marked on map |
| 11. | 4.7 |  | Right turn onto road - Immediately before water tower, turn R into Arnolds Farm Lane. Minor roads | L | A, D, E, J, K | 23 | n/a |
| 12. | 4.7 – 5.4 |  | Arnolds Farm Lane. Small, quiet road. | L | A, D, E, J, K | 23 | n/a |
| 13. | 5.4 |  | T-junction. Turn L at T-junction into Lower Road and across junction. Runners have traffic behind them so risk from cars turning left | H | A, B, C, D, E, I, J, K | 23 | Marshals. Caution boards Hazard marked on map. |
| 14. | 5.4 – 6.3 |  | Road - Minor road. Quiet road on LHS at 5.45 miles | L | A, D, E, K | 23 | n/a |
| 15. | 6.25 |  | T-junction - Turn left at T-junction into Rayleigh Road. Run on pavement on LHS | L | A, I, J | 23 | n/a |
| 16. | 6.25 – 6.7 |  | Pavement. Residential with some minor residential roads from LHS | L | A, I, J | 23 | n/a |
| 17. | 6.7 |  | Road crossing. Turn R to cross road and turn right down Hutton Lane. Good visibility, urban road | M | A, B, C, D, E, I, J, K | 11, 23 | Marshals. Hazard marked on map. |
| 18. | 6.7 – 7.0 |  | Pavement - Hutton Lane. Run along pavement on LHS of road | L | A, D, E, K | 23 | n/a |
| 19. | 7.0 – 7.2 |  | Path - Just before road turns sharp R, turn L onto signed FP. After just a few yards, turn R onto FP | L | A, J | 23, 28 | n/a |
| 20. | 7.2 |  | Cross road. Thru small car park and R along road past Hutton Church. Immediately past church, turn L onto FP signed “Footpath 94 to Bridleway 72” | L | A, D, E, I, J, K | 23, 28 | n/a |
| 21. | 7.2 – 7.45 |  | Path - SO on FP across field | L | A, J | 23, 28 | n/a |
| 22. | 7.45 |  | Cross farm lane - SO across lane onto track, signed “Bridleway 72 to Ingrave” | L | A, D, E, J, K | 23, 28 | n/a |
| 23. | 7.45 – 8.8 |  | Lane / farm track - Follow farm track SO for 0.35 miles. With farmhouse to LHS, turn R along lane / narrow road. Eventually past water works and Ingrave Hall – Very quiet road. | L | A, D, E, J, K | 23, 28 | n/a |
| 24. | 8.8 – 9.5 |  | Road / Pavement - On narrow road to Ingrave, then on pavement thru Ingrave–“Middle Road” | L | A, D, E, I, J, K | 23 | n/a |
| 25. | 9.5 |  | Road crossing. At T-junction cross A128 (Brentwood Road) and turn L along pavement. Good visibility with crossing, busy road | H | A, B, C, D, E, I, J, K | 11, 23 | Marshals. Caution boards Hazard marked on map. |
| 26. | 9.5 - 9.6 |  | Pavement / Lane - Along pavement for 50m then R into Thorndon Gate - Road to golf club | L | A, B, C, D, E, I, J, K | 23, 28 | n/a |
| 27. | 9.6 |  | Path - Immediately after entrance to Thorndon Hall turn half R onto “Public Footpath 42” and thru trees | L | A, B, C, D, E, I, J, K | 23, 28 | n/a |
| 28. | 9.6 – 10.3 |  | Path - SO on paths to Thorndon Park | L | A, J | 23, 28 | n/a |
| 29. | 10.3 – 10.9 |  | Road / Lane - Turn R onto quiet road thru Thorndon Park | L | A, D, E, I, J, K | 23, 28 | n/a |
| 30. | 10.9 |  | Car park - Finish on road next to entrance to Visitor’s Centre. | L | A, B, C, D, E, I, J, K | 11, 23 | Marshals to ensure area is cleared after finish |

Green Belt Relay - Risk Assessment

Leg 13  -    Thorndon Park North Countryside Centre  to  Cranham (Jobber’s Rest)) 6.6 miles

| Course Identification | Green Belt Relay Stage 13 |  |  | A | B | C | D |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Whole event codes (1-8),(17, 29 & 31): 3, 4, 5, 7, 8, 17, 29, 31 |  |  |  | H/M/L | A to H | 9 to 30 only | R=Right, L=Left, SO=Straight On, FP=Footpath, FB=Footbridge |
| ID No | Miles from start | Details of hazard |  | Risk Rating level H/M/L | Persons at risk from hazard |  | Additional measures to reduce risk to LOW, with name of person or official function who will reduce the risk to low (if applicable) |
|  |  | Symbol | Desc |  |  |  |  |
| 1. | 0.0 |  | Start - Start on road in park just north of Visitor’s Centre. | L | A, B, C, D, E, I, J, K | 11, 23 | n/a |
| 2. | 0.0 – 0.2 |  | Road in park - Go west along road to exit park gates | L | A, B, C, D, E, I, J, K | 23 | n/a |
| 3. | 0.2 – 0.3 |  | Path - After exiting park, stay L / SO onto FP. Follow FP for 70m then turn R to road | L | A, J, N | 23, 28 | n/a |
| 4. | 0.3 |  | Cross straight over Childerditch Lane. Limited visibility, but traffic stopping for junction, and runners still all together at this point | M | A, B, C, D, E, J, K, N | 11, 23 | Marshals, checked by control car Caution boards Hazard marked on map. |
| 5. | 0.3 – 0.85 |  | Path along Eagle Way | L | A, J, N | 23, 28 | n/a |
| 10. | 0.85 |  | Pavement - Turn L into Clive Road. Stay on LHS pavement | L | A, I, J | 23 | n/a |
| 11. | 0.85 - 1 |  | Path - At T-junction stay L then L onto lane behind Ford. After 20m turn R onto path thru woods, signed Warley Gap. After 100m at junction of FPs go L | L | A, J, N | 23 |  |
| 13. | 1 - 1.7 |  | Path - Warley Gap | L | A, J, N | 23 | n/a |
| 14. | 1.7 |  | Road Crossing - Out onto road (Magpie Lane). Cross straight over into Bird Lane. Poor visibility. | H | A, B, C, D, E, J, K, N | 11, 23 | Marshals Caution Boards Hazard marked on map. |
| 15. | 2.2 – 2.8 |  | Road - Turn L at T-junction into Bird Lane | L | A, D, E, K | 23 | n/a |
| 16. | 2.3 |  | Road Crossing - At T-junction turn right then L to cross over into Codham Hall Lane. Good visibility | H | A, B, C, D, E, J, K, N | 11, 23 | Marshals Caution Boards Hazard marked on map. |
| 17. | 2.3 – 2.85 |  | Lane - Codham Hall Lane | L | A, D, E, K | 23 | n/a |
| 18. | 2.85 – 3.6 |  | Path / Bridleway - SO into field at green metal gate and then R onto bridleway around field, then through woods | L | A, I, J, N | 23 | n/a |
| 20. | 3.6 – 3.9 |  | Road / Bridleway - Out of woods, turn R along road and SO up to FB and over A127 | L | A, B, C, D, E, J, K, N | 23 | n/a |
|  | 3.9 – 4.85 |  | R off FB and onto wide track downhill. After 400m turn L on track with M25 above to your RHS | L | A, B, C, D, E, J, K, N | 23 | n/a |
| 22. | 4.85 – 5.5 |  | Path - R thru tunnel / FP under M25. Go SO with rail to LHS and on FP thru wood. Exit wood and veer L across grass | L | A, J, I | 23 | n/a |
| 23. | 5.3 |  | Turn right to path (ignoring railway crossing) and take path between houses | L | A, I | 11, 23 | n/a |
| 24. | 5.5 |  | Path emerges between houses, cross Heron Way (quiet residential road) | L | A, B, C, D, E, J, K, N |  | Marshals |
| 25. | 5.5 – finish |  | Pavement to finish over road from Jobber’s Rest | L |  | 11, 23 | n/a |

Green Belt Relay - Risk Assessment

Leg 14  -  Cranham to Davy Down     8.2 miles

| Course Identification | Green Belt Relay Stage 14 |  |  | A | B | C | D |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Whole event codes (1-8),(17, 29 & 31): 3, 4, 5, 7, 8, 17, 29, 31 |  |  |  | H/M/L | A to H | 9 to 30 only | R=Right, L=Left, SO=Straight On, FP=Footpath, FB=Footbridge |
| ID No | Miles from start | Details of hazard |  | Risk Rating level H/M/L | Persons at risk from hazard |  | Additional measures to reduce risk to LOW, with name of person or official function who will reduce the risk to low (if applicable) |
|  |  | Symbol | Desc |  |  |  |  |
| 1. | 0.0 |  | Start - Start FP beside golf course | L | A, I, J | 10, 11, 23 |  |
| 2. | 0.0 – 1.62 |  | Footpath | L | A, I, J | 11, 23 | n/a |
| 3. | 1.63 – 1.9 |  | Concrete farm track | L | A, B, C, D, E, J, K, N | 11, 23 |  |
| 4. | 1.9 |  | # Road crossing (40mph zone, limited visibility from west) | H | A, I, J | 23 | Marshals on both sides of road CAUTION RUNNERS boards Enforced sharp left turn to prevent runners from dashing across and to run away from blind corner) Briefing to runners and hazard marked on map |
| 5. | 1.9 – 2.4 |  | Pavement into North Ockendon | L | A, B, C, I, J, K | 11, 23 | n/a |
| 6. | 2.4 |  | Road crossing into Fen Lane (30mph zone, good visibility) | M |  |  | Marshals on both sides of road CAUTION RUNNERS boards Briefing to runners and hazard marked on map |
| 7. | 2.4 – 3.75 |  | Running on road (30mph zone) | M |  |  | Runners briefed to take care |
| 8. | 3.75 – 8 miles |  | Footpaths | L |  |  | n/a |
| 9. | 8 miles |  | Road crossing (at traffic island at mini roundabout) | M |  |  | Marshals on both sides of road CAUTION RUNNERS boards Briefing to runners and hazard marked on map |
| 10. | 8.1 – 8.5 |  | Footpaths | L |  |  | n/a |

Green Belt Relay - Risk Assessment

Leg 15 -  Stone Hall Bowls Club, Dartford to  Lullingstone Park  9.4 miles

| Course Identification | Green Belt Relay Stage 15 |  |  | A | B | C | D |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Whole event codes (1-8),(17, 29 & 31): 3, 4, 5, 7, 8, 17, 29, 31 |  |  |  | H/M/L | A to H | 9 to 30 only | R=Right, L=Left, SO=Straight On, FP=Footpath, FB=Footbridge |
| ID No | Miles from start | Details of hazard |  | Risk Rating level H/M/L | Persons at risk from hazard |  | Additional measures to reduce risk to LOW, with name of person or official function who will reduce the risk to low (if applicable) |
|  |  | Symbol | Desc |  |  |  |  |
| 1. | 0.0 |  | Pavement - Start on pavement on west side of Cotton Mill Lane, opposite bowls club | L | A, B, C, D, E, I, J, K | 11, 13 | n/a |
| 2. | 0.0 – 0.2 |  | Pavement - On pavement on RHS of Cotton Mill Lane | L | A, B, C, D, E, I, J, K | 11, 23 | n/a |
| 3. | 0.2 – 0.65 |  | Pavement - R on pavement along A226 | L | A, I, J | 23 | n/a |
| 4. | 0.4 |  | Road crossing - Cross Invicta Road to RHS – minor residential road | L | A, D, E, I, J, K |  | n/a |
| 5. | 0.45 |  | Road crossing - Cross Milestone Road to RHS – minor residential road | L | A, D, E, I, J, K |  | n/a |
| 6. | 0.46 |  | Zebra Crossing - Use zebra crossing to cross London Road and turn R along pavement | L | A, D, E, I, J, K | 23 | n/a |
| 7. | 0.65 – 0.75 |  | Cycle path - Immediately over M25, turn L onto cycle path. | L | A, I, J, K | 23 | n/a |
| 8. | 0.75 |  | Road crossing / Pavement - Turn R along pavement (Watling Street), then L into Pilgrims Way. Stay on LHS pavement along Pilgrims Way | M | A, B, C, D, E, I, K | 11, 23 | Hazard marked on maps Marshals |
| 9. | 0.75 – 1.0 |  | Pavement / Road crossing - Pavement on LHS of Pilgrims Way. Minor residential road to L at 0.85 miles (Wayville Road) | L | A, D, E, I, J, | 23 | n/a |
| 10. | 1.0 |  | Footbridge - Turn L to climb to FB, R over FB and L to descend at opposite side | L | A, B, C, I, J | 11, 23 | n/a |
| 11. | 1.05 – 1.57 |  | Double back and run down Princes Road on pavement | L | A, B, C, D, E, I, J, K | 11, 23 | Marshals |
| 12. | 1.57 – 1.7 |  | Cross Darenth Road and turn right into Powder Mill Lane – steep descent | M | A, B, C, D, E, I, J | 23 | Hazard marked on maps Marshals |
| 13. | 1.7 – 2.3 |  | Darenth Valley path | L | A, I, J, K | 23 | n/a |
| 14. | 2.3 – 2.6 |  | Pavement along Hawley Road | L | A, I, J, K | 23 | n/a |
| 15. | 2.6 |  | Very narrow short footpath | M | A, I, J, K | 23 | Marshals to guide and warn pedestrians |
| 16. | 2.6 – 3.0 |  | Footpath | L | A, I, J, K | 23 | n/a |
| 17. | 3.0 – 3.25 |  | Cul-de-sac | L | A, I, J, K | 23 | n/a |
| 18. | 3.25 |  | Busy road crossing onto footpath opposite | H | A, B, C, D, E, I, J, K | 11,23 | Hazard marked on maps Marshals Caution boards |
| 19. | 3.25 – 4.2 |  | Footpath | L | A, I, J, K | 23 | n/a |
| 20. | 4.2 – 4.3 |  | Road / pavement - At T-junction turn R on pavement thru South Darenth Village | L | A, D, E, I, J, K | 23 | n/a |
| 21. | 4.34 |  | Road crossing - Cross over Devon Road to RHS and SO staying on RHS pavement | L | A, B, C, D, E, I, J, K | 23 | vn/a |
| 22. | 4.6 – 4.65 |  | Road junction / crossing - Under viaduct and turn R, at Bridges Pub into Station Road. Stay on RHS pavement over river, then turn L left to cross road & down onto path along river (signed Darent Valley Path). | M | A, B, C, D, E, I, J, K | 11, 23 | Hazard marked on maps Marshals Caution boards |
| 23. | 4.65 – 5.6 |  | Path - Darent Valley Path (DVP) | L | A, I, J, K | 23, 28 | n/a |
| 24. | 5.67 – 5.8 |  | Road / Lane - Path comes up to lane. Turn L along Franks Lane. | L | A, D, E, J, K | 23 | n/a |
| 25. | 5.8 |  | Path - Turn R thru wooden KG onto path, next to cricket pitch. Signed DVP | L | A, I, J, K | 23 | n/a |
| 26. | 5.8 – 6.75 |  | Path - Darent Valley Path can be a bit uneven underfoot. | M | A, I, J, K | 23 | Starters Briefing. |
| 27. | 6.75 |  | Road / Pavement - Through pub beer garden and R onto Farningham High Street. | M | A, B, C, D, E, I, J, K | 11, 23 | Hazard marked on maps Marshals |
| 29. | 6.85 |  | Road junction - Turn L into Sparepenny Lane. Narrow, quiet road | L | A, D, E, K | 23 | n/a |
| 30. | 6.85 – 7.8 |  | Road - Sparepenny Lane. | L | A, D, E, I, J, K | 23 | n/a |
| 31. | 7.8 |  | T-junction - Turn right towards Roman Villa (Lullingstone Lane). Quiet lane. | L | A, B, C, D, E, I, J, K | 11, 23 | n/a |
| 32. | 7.8 - 8.5 |  | Road - Lullingstone Lane. Narrow, quiet road | L | A, D, E, J, K | 23 | n/a |
| 33. | 8.5 – 8.6 |  | Car park / Villa - Stay SO on road past Roman Villa and SO on lane to Lullingstone Castle | L | A, B, C, D, E, I, J, K | 11, 23, 28 | n/a |
| 34. | 8.6 – 8.9 |  | Lane - Lane to, and past, castle | L | A, D, E, J, K | 23, 28 | n/a |
| 35. | 8.9 – 9.4 |  | Path - Darent Valley Path to Lullingstone Visitors Centre | L | A, D, E, I, J, K | 23 | n/a |
| 36. | 9.4 |  | Finish - Finish on path next to River Darent and behind Lullingstone Visitor’s Centre | L | A, D, E, I, J, K | 23 | n/a |

Green Belt Relay - Risk Assessment

Leg 16  -    Lullingston Park Visitors Centre    to    Tatsfield    13.3 miles

| Course Identification | Green Belt Relay Stage 16 |  |  | A | B | C | D |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Whole event codes (1-8),(17, 29 & 31): 3, 4, 5, 7, 8, 17, 29, 31 |  |  |  | H/M/L | A to H | 9 to 30 only | R=Right, L=Left, SO=Straight On, FP=Footpath, FB=Footbridge |
| ID No | Miles from start | Details of hazard |  | Risk Rating level H/M/L | Persons at risk from hazard |  | Additional measures to reduce risk to LOW, with name of person or official function who will reduce the risk to low (if applicable) |
|  |  | Symbol | Desc |  |  |  |  |
| 1. | 0.0 – 0.2 |  | Path - Soon FP along LHS of field | L | A, B, C | 11, 23 | n/a |
| 2. | 0.2 |  | Road - Follow FP out of field, down steps and veer L to cross Castle Road (quiet road) and back onto DVP | M | A, D, E, K | 11, 23 | Marshals Caution boards (note: pack all together at this point) |
| 3. | 0.2 – 1.25 |  | Path - Follow Darent Valley Path (DVP) thru fields to Shoreham | L | A, J, K, M | 23 | n/a |
| 4. | 1.25 – 1.35 |  | Lane - Path along river to lane then L along lane and over footbridge | L | A, D, E, J, K | 23 | n/a |
| 5. | 1.35 – 1.55 |  | Path - Over FB and turn R to Darent Valley Path along river | L | A, I, J, K | 23 | na |
| 6. | 1.55 – 1.6 |  | Road - Darent Valley Path comes out to road (Darent Way) – go SO | L | A, D, E, I, J, K | 23 | n/a |
| 7. | 1.6 |  | T-junction - SO past road bridge to RHS | L | A,D E I, J, K | 23 | n/a |
| 8. | 1.6 – 1.8 |  | Road - SO along Church Street, Shoreham Village. Small, quiet road | L | A,B, D, E, I, J, K | 23 | n/a |
| 9. | 1.8 – 2.0 |  | Path - Turn R onto enclosed FP, signed Darent Valley Path. | L | A, I, J | 23, 28 | n/a |
| 10. | 2.0 – 2.1 |  | Golf Course - SO to follow DVP across Shoreham Golf Club – runners cross fairway. The Golf Club is aware of relay. | M | A, I, J, K, P | 11, 23, 28 | Inform golf club Remind runners at briefing Hazard marked on map |
| 11. | 2.1 – 3.0 |  | Path - Go SO over lane and on track / bridleway to Otford | L | A, I, J, K, N | 23, 28 | n/a |
| 12. | 3.0 – 3.2 |  | Lane - SO along bridleway / lane to Otford | L | A,D,E,J,K,N | 23 | n/a |
| 13. | 3.2 |  | T-junction - Turn right onto Otford High Street. Use pavement on RHS | M | A, B, C, D, E, I, J, K | 11, 23 | Marshals |
| 14. | 3.2 – 3.8 |  | Pavement - Otford High Street | L | A, I, J | 23 | n/a |
| 15. | 3.3 |  | Car park entrance - Car park entrance from right | L | A, B, C, D, E, I, J, K | 11, 23 | n/a |
| 16. | 3.8 |  | Road crossing - Turn L to cross High Street and into Telston Lane. Now on North Downs Way (NDW) | M | A, D, E, I, J, K | 23, 11 | n/a |
| 17. | 3.8 – 4.2 |  | Road / Lane - SO along residential road staying on LHS pavement. 2 quiet residential roads come from LHS. Stay SO on Telston Lane as it narrows and what looks like main road turns R | L | A, D, E, I, J, K | 23 | n/a |
| 18. | 4.0 |  | Lane - Follow lane R then L past farm (NDW) | L | A, D, E, I, J, K | 23 | n/a |
| 19. | 4.2 |  | Footbridge over rail - FB over railway and SO across fields (NDW) | L | A, D, I, J, K | 23 | n/a |
| 20. | 4.2 – 4.7 |  | Path - North Downs Way across fields. | L | A, J, K, M, K | 23, 28 | n/a |
| 21. | 4.7 |  | Pavement - Left onto pavement next to along London Road at Doddington Manor Hotel – run on LHS | L | A, I, J K | 23 |  |
| 22. | 4.7 – 4.75 |  | Pavement | L | A, B, C, K | 11, 23 | London Road, Dunton Green |
| 23. | 4.75 |  | Road crossing - Opposite Rose & Crown Pub turn R to cross London Road, then after pub turn R on pavement along Morants Court Road. Stay on RHS | M | A, B, C, D, E, I, J, K | 11, 23 | Marshals Caution board Hazard marked on map |
| 24. | 4.75 – 5.3 |  | Pavement / road - Morants Court Road – run on pavement on RHS | L | A, D, E, I, J, K | 23 | n/a |
| 25. | 5.25 – 5.3 |  | Road crossing - Turn L to cross over Morants Court Road, then R on pavement over M25 bridge | M | A, B, C, D, E, I, J, K | 11, 23 | Marshals Caution boards Hazard marked on map |
| 26. | 5.3 |  | Road junction - Turn L onto B2211, signed Sundridge and NDW – stay on LHS | L | A, D, E, K | 23 | n/a |
| 27. | 5.3 – 5.8 |  | Road / pavement - Run on LHS – narrow pavement in places. Can be busy road | M | A, D, E, K | 23 | Marshals, caution boards |
| 28. | 5.8 |  | Road crossing. Around bend after farm and just before cottages, turn R to cross road and over wooden stile, next to metal gate, signed FP. Poor visibility and fast road | H | A, B, C, D, E, I, J, K | 10, 11, 23 | Marshals to get runners over to RHS prior to the bend, another to guide over stile, and another to watch traffic round bend. Caution boards. Hazard marked on maps. |
| 29. | 5.8 – 6.2 |  | Path - SO along track / FP to Chevening Church. | L | A, I, J, K | 23, 28 | n/a |
| 30. | 6.2 |  | Churchyard - Turn R to go around outside of churchyard, follow to L and after a few yards turn R onto enclosed FP going north from church. NOTE: it is Sunday morning and a service is taking place at the church. Vehicles are parked next to path so TAKE CARE | L | A, E, I, J, K | 23, 28 | n/a |
| 31. | 6.2 – 6.6 |  | Path - FP thru Chevening Park | L | A, I, J, K | 23, 28 | n/a |
| 32. | 6.6 – 6.9 |  | Road - After field to LHS, turn L along road, then L and just before road turns R, turn sharp R onto grass path uphill - Narrow, quiet, private road | L | A, D, E, K | 23, 28 | n/a |
| 33. | 6.9 – 7.5 |  | Path - Into field and L along LHS of field - Chevening Park. At other end of field cross over lane and SO along RHS of field. At end veer R to climb over stile and RHS of field steeply uphill. At top go SO over stile and still steeply uphill. After going thru woods and at very top of hill, turn L onto wide track. | L | A, I, J, K | 23, 28 | n/a (brief runners if there is likely to be livestock – they can get close to the path. Course markers to contact timekeepers for briefing if it is likely to be a problem) |
| 34. | 7.5 |  | T-junction - Past Keepers Cottage and turn L onto narrow, quiet road (Sundridge Hill) | L | A, D, E, J, K | 11, 23 | n/a |
| 35 | 7.5 - 8.0 |  | Road - Steep downhill on narrow, quiet road | L | A, D, E, K | 23 | n/a |
| 36. | 8.0 |  | Road junction - Turn R onto Pilgrims Way. Narrow, quiet roads | L | A, D, E, K | 23 | n/a |
| 37. | 8.0 – 8.8 |  | Road - Pilgrims Way - Narrow, quiet road | L | A, D, E J, K | 23 | n/a |
| 38. | 8.8 |  | Road junction - Right at T-junction, then immediately left, still on Pilgrim’s Way. | L | A, D, E, J, K | 23 | n/a |
| 39. | 8.8 – 10.8 |  | Road - Pilgrims Way | L | A, D, E, I, J | 23 | n/a |
| 40. | 9.4 |  | crossroads - Very minor, quiet crossroads | L | A, D, E, J, K | 23 | n/a |
| 41. | 10.0 |  | T-junction - Minor, quiet road from left | L |  | 23 | n/a |
| 42. | 10.2 |  | T-junction - Minor, quiet road from right | L | A, D, E, J, K | 23 | n/a |
| 43. | 10.8 – 10.9 |  | crossroads - Right onto A233, crossing over asap (then turn L into “The Avenue” after 150m – see note 45. below). Good visibility, plenty of time to cross, but busy fast road | H | A, B, C, D, E, J, K | 11, 23 | Marshals Hazard marked on map Caution boards |
| 45. | 10.9 – 12.3 |  | Private road / track - Turn L into the Avenue. Very exclusive private road. North Downs Way. | L | A, D, E, I, J, K | 11, 23, 28 | n/a |
| 46. | 11.6 |  | Private Road Junction - Road turns R and after 70m turn L onto private road (Chestnut Avenue) | L | A, D, E, I, J, K | 23 | n/a |
| 47. | 12.3 |  | T-junction - Turn right at junction into Church Hill | M | A, B, C, D, E, J, K | 10, 11, 23 | Marshals Caution boards Hazard marked on map |
| 48. | 12.3 – 12.8 |  | Road - Church Lane. Narrow quiet road but NO PAVEMENT | M | A, B, C, D, E, J, K | 10, 23 | Caution boards |
| 49. | 12.8 |  | Road junction - Turn left into Ship Hill | M | A, B, C, D, E, J, K | 10, 11, 23 | Marshals Caution boards Hazard marked on map |
| 50. | 12.8 – 13.3 |  | Road - Run along pavement on LHS of Ship Hill | L | A, D, E, J | 23 | n/a |
| 51. | 13.05 |  | Road crossing - As pavement stops cross over road and run on pavement on RHS | L | A, D, E, J, K |  | n/a |
| 52. | 13.3 |  | Road junction / crossing - Cross over road to finish at horse trough on green outside Old Ship Pub | M | A, B, C, D, E, I, J, K | 11, 23 | Marshals Caution boards Hazard marked on map |

Green Belt Relay - Risk Assessment

Leg 17  -     Tatsfield    to    Merstham         10.5  miles

| Course Identification | Green Belt Relay Stage 17 |  |  | A | B | C | D |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Whole event codes (1-8),(17, 29 & 31): 3, 4, 5, 7, 8, 17, 29, 31 |  |  |  | H/M/L | A to H | 9 to 30 only | R=Right, L=Left, SO=Straight On, FP=Footpath, FB=Footbridge |
| ID No | Miles from start | Details of hazard |  | Risk Rating level H/M/L | Persons at risk from hazard |  | Additional measures to reduce risk to LOW, with name of person or official function who will reduce the risk to low (if applicable) |
|  |  | Symbol | Desc |  |  |  |  |
| 1. | 0.0 – 0.8 |  | Road - Start on Approach Road, Westmore Green, near Old Ship Pub. Run on LHS of road | L | A, B, C, D, E, I, J, K | 23 | n/a |
| 2. | 0.8 |  | T-junction - Turn R at T-junction along B2024 (Clarks Lane). Remain on right | M | A, B, C, D, E, I, K | 11, 23 | Marshals Hazard marked on map Caution boards |
| 3. | 0.8 – 1.55 |  | Road - Clarks Lane | L | A, D, E, I, J, K | 23 | n/a |
| 4. | 0.82 |  | Lane from LHS - Minor lane from left, White Lane | L | A, D, E, I, J, K |  | n/a |
| 5. | 1.0 |  | Road from RHS - Minor road from right, Beddlestead Lane | L | A, D, E, I, K |  | n/a |
| 6. | 1.55 |  | Road junction – Cross B269 at roundabout, then immediately left into The Ridge. Good visibility and traffic slowed for roundabout | H | A, B, C, D, E, I, J, K | 11, 23 | Marshals Hazard marked on map Caution boards |
| 7. | 1.55 – 3.3 |  | Road - Minor lane from left at 2.4 miles. | L | A, D, E, J, K | 23 | n/a |
| 8. | 3.3 |  | T-junction - Left turn into Gangers Hill | M | A, B, C, D, E, J, K | 11, 23 | Marshals Hazard marked on map Caution boards |
| 9. | 3.3 – 4.7 |  | Road - Steep downhill, narrow, winding, quiet road | L/M | A, D, E, J, K | 23 | Caution boards |
| 10. | 3.85 |  | Road from LHS - Minor road from LHS – Tandridge Hill Lane | L | A, D, E, J, K | 23 | Caution boards |
| 11. | 4.7 |  | Y-junction - Turn sharp R up track / lane – Quarry Road, signed bridleway. | L | A, B, C, D, E, J, K | 11, 23, 28 | n/a |
| 12. | 4.7 – 5.0 |  | Track - Traffic is almost nil | L | A, D, E, J, K | 23, 28 | n/a |
| 13. | 5.0 |  | T-junction - Isolated area, track and bridleway make up junction. Turn L onto NDW | L | A, D, E, I, J, K | 23, 28 | n/a |
| 14. | 5.0 – 5.25 |  | Bridleway - North Downs Way (NDW) above Godstone Vineyard | L | A, J, K,N M | 4, 11, 23, 28 | n/a |
| 15. | 5.25 – 5.5 |  | Road - Quiet dead-end road, some houses and a warehouse | L | A, D, E, I, J, K | 23 | n/a |
| 16. | 5.5 |  | Sharp turn R - Sharp right up steps onto path through woods – North Downs Way | L | A, J, K | 23, 28 | n/a |
| 17. | 5.4 – 5.65 |  | Path - Sunken track / Roman road | L | A, D, E, J, K | 23, 28 | n/a |
| 18. | 5.65 – 5.85 |  | Path - Turn L thru field North Downs Way ad over footbridge. | L | A, J, K, M | 23, 28 | n/a |
| 19. | 5.85 – 6.3 |  | Path - Over FB and L onto FP signed NDW. Near top go L and stay L at junction of FPs | L | A, J, K | 23, 28 | n/a |
| 20. | 6.3 – 6.4 |  | Picnic area - SO thru view point, runners can run on path thru’ picnic area | L | A, B, I, J, K | 23 | n/a |
| 21. | 6.4 |  | Onto Road - Onto road and SO along staying on LHS | L | A, J, K, N, M | 4, 23 | n/a |
| 22. | 6.4 – 7.6 |  | Road - Minor quiet road past Gravelly Hill | L | A, D, E, I, J K | 23 | n/a |
| 23. | 7.1 |  | Road junction - Narrow, quiet lane from left – Hextalls Lane | L | A, E, J, K | 23 | n/a |
| 24. | 7.6 |  | Road crossing - Turn R at T-junction into Stanstead Rd, then L to follow NDW into driveway to Willey Park Farm | M | A, B, C, D, E, J, K, N | 11, 23, 28 | Marshals Hazard marked on map Caution boards |
| 25. | 7.6 – 8.7 |  | Track / lane - Turn L at minor junction, still on North Downs Way | L | A, J, K, N | 23, 28 | n/a |
| 26. | 8.7 |  | Road crossing - Cross straight over Hilltop Lane, TAKE CARE onto BW. Quiet narrow road | M | A, D, E, J, K | 23, 28 | Marshals Hazard marked on map Caution boards |
| 27. | 8.7 – 9.0 |  | Path - North Downs Way | L | A, J, K, N | 23, 28 | n/a |
| 28. | 9.0 – 9.75 |  | Path - North Downs Way, thru’ crop field, under motorway and thru’ field | L | A, I, J, K | 23, 28 | n/a |
| 29. | 9.75 |  | Road - Right off path onto Rockshaw Road. Run on pavement on LHS | L | A, B, C, D, E, I, J, K | 11, 23 | n/a |
| 30. | 9.75 – 10.4 |  | Road / pavement - Narrow quiet road, runners can use pavement, but very narrow over railway bridge at 10.3 miles | L | A, D, E, I, J, K | 23 | n/a |
| 31. | 10.4 |  | T-junction - Left on pavement along A23 | L | A, I, J, K | 23 | n/a |
| 32. | 10.4 – 10.5 |  | Pavement - Pavement on LHS of A23 | L | A, I, J, K | 23 | n/a |
| 33. | 10.5 |  | Road – turn into Station Rd and finish by the village club | L | A, B, C, D, E, I, J K | 23 | n/a |

Green Belt Relay - Risk Assessment

Leg 18  -     Merstham to Burford Bridge       9.7 miles

| Course Identification | Green Belt Relay Stage 18 |  |  | A | B | C | D |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Whole event codes (1-8),(17, 29 & 31): 3, 4, 5, 7, 8, 17, 29, 31 |  |  |  | H/M/L | A to H | 9 to 30 only | R=Right, L=Left, SO=Straight On, FP=Footpath, FB=Footbridge |
| ID No | Miles from start | Details of hazard |  | Risk Rating level H/M/L | Persons at risk from hazard |  | Additional measures to reduce risk to LOW, with name of person or official function who will reduce the risk to low (if applicable) |
|  |  | Symbol | Desc |  |  |  |  |
| 1. | 0.0 – 0.2 |  | Path - Path from Quality St, Merstham to Reigate Hill Golf Course. Cricket pitch on L.H.S. North Downs Way. | L | A, B, C, I, J, K | 23 | n/a |
| 2. | 0.2 – 0.5 |  | Path - SO across Reigate Hill Golf Course. North Downs Way . | L | A, I, J, K, P | 23, 28 | Inform golf club. Hazard marked on maps |
| 3. | 0.5 |  | Road crossing - SO over minor lane to Golf Clubhouse. | L | A, B, D, E, I, J, K, P | 11, 23 | n/a |
| 4. | 0.5 – 0.55 |  | Path - Across Reigate Hill Golf Course.NDW | L | A, I, J, K, P |  | n/a |
| 5. | 0.55 – 0.75 |  | Path - SO past golf tee & thru KG onto path | L | A, J, K, P |  | n/a |
| 6. | 0.75 |  | Road junction - Path turns into lane. Comes up to t-junction with Rocky Lane | L | A, B, C, D, E, I, J, K | 11, 23 | n/a |
| 7. | 0.75 – 0.8 |  | Road - Turn R along Rocky Lane. Cross over to run on LHS. | M | A, D, E, I, J, K | 23 | Caution board |
| 8. | 0.8 – 1.5 |  | Road - L onto minor, quiet road thru’ grounds of school. After 250m turn R at church to stay on NDW. | L | A, D, E, J, I, K | 23 | n/a |
| 9. | 1.5 – 2.2 |  | Bridleway - L onto BW - North Downs Way. After 250m take R at Y-junction of paths | L | A, I, J, K, N | 23 | n/a |
| 10. | 2.2 |  | Road crossing - Cross SO Wray Lane (narrow road) to car park. | M | A, B, C, D, E, I, J, K | 11, 23 | Caution board |
| 11. | 2.2 – 2.3 |  | Road - Wray Lane car park, Reigate Hill. SO thru car park and up to FB over road | M | A, B, C, D, E, J, K | 11, 28 | n/a note: on the other hand, there’s little danger in this bit. |
| 12. | 2.3 – 3.7 |  | Path - SO along North Downs Way | L | A, I, J, K, N | 23, 28 | n/a |
| 13. | 3.7 – 3.9 |  | Very steep descent down NDW | L | A, D, E, J, K, N | 23, 28 | Marked on maps |
| 14. | 3.9 – 5.8 |  | NDW footpath around fields | L | A, D, E, I, J, K, N | 23 | n/a |
| 15. | 5.8 |  | NDW emerges to Pebble Hill Rd. Runners follow pavement then cross. Busy road with limited visibility. | H | A, D, E, I, J, K, N | 23, 28 | Marshals Hazard marked on map Caution boards |
| 16. | 5.8 – 6.3 |  | NDW runs adjacent to road, then into The Coombe (quiet residential road) | L | A, I, J, K, N | 23, 28 | n/a |
| 17. | 6.3 – 7.3 |  | NDW footpath through fields and woods | L | A, J, K, N | 23, 28 | n/a |
| 18. | 7.4 |  | Road crossing – emerge from NDW and cross to RHS of Boxhill Rd | M | A, D, E, I, J, K, N | 23,28 | Marshals Hazard marked on map Caution boards |
| 19 | 7.4 – 8.15 |  | Pavement along busy road with lots of parked cars | L | A, J, K, N | 23, 28 | n/a |
| 20. | 8.15 |  | Road crossing – cross to path by LHS of Boxhill Rd | M | A, D, E, I, J, K, N | 23,28 | Marshals Hazard marked on map Caution boards |
| 21 | 8.15 – 9.57 |  | Footpath, steep descent, some livestock | L | A, J, K, N | 23, 28 | Descent marked on map |
| 22 | 9.57 – 9.7 |  | Finish on slow but often very crowded road | M | A, D, E, I, J, K, N | 23,28 | Marshals Hazard marked on map Caution boards |

Green Belt Relay - Risk Assessment

Leg 19  -     Burford Bridge to West Hanger        8.4  miles

| Course Identification | Green Belt Relay Stage 19 |  |  | A | B | C | D |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Whole event codes (1-8),(17, 29 & 31): 3, 4, 5, 7, 8, 17, 29, 31 |  |  |  | H/M/L | A to H | 9 to 30 only | R=Right, L=Left, SO=Straight On, FP=Footpath, FB=Footbridge |
| ID No | Miles from start | Details of hazard |  | Risk Rating level H/M/L | Persons at risk from hazard |  | Additional measures to reduce risk to LOW, with name of person or official function who will reduce the risk to low (if applicable) |
|  |  | Symbol | Desc |  |  |  |  |
| 1. | 0 – 0.9 |  | Road / pavement - Thru’ West Humble Village. Beware of entrance to pub car park, residential roads and private drives. | L | A, D, E, I, J, K | 23 | Marshals to avoid need to mark turns |
| 10. | 0.9 – 1.2 |  | T – junction - Turn left up lane next to Chapel Ruins - National Trust. | L | A, D, E, I, J, K, N | 23 | n/a |
| 11. | 1.2 – 2.3 |  | Track / drive - Up narrow, quiet track to meet North Downs Way | L | A, D, E, J, K, N | 23, 28 | n/a |
| 13. | 2.4 – 2.9 |  | NDW follows quiet road in Ranmore | L | A, J, K, N | 23 | n/a |
| 14. | 2.9 |  | Road crossing – runners cross Ranmore Common Rd | L | A, D, E, I, J, K, N | 11, 23 | Marshals Caution boards Hazard marked on map |
| 15. | 3.0 – 5.2 |  | Path - North Downs Way | L | A, J, K, N | 23 | n/a |
| 21. | 5.2 |  | Road Crossing - Right onto road. After 20 metres, left onto path. Still on North Downs Way. Quiet road with sharp bend to slow runners down | M | A, B, C, D, E, J, K, N | 11, 23, 28 | Marshals Caution boards Hazard marked on map |
| 22. | 5.2 – 8.2 |  | Track - Follow North Downs Way. Pass Hollister Farm at 8.2 miles. | L | A, D, E, J, K, N | 23, 28 | n/a |
| 23. | 8.4 |  | Cross Combe Lane. Quiet road, but a bend limits visibility. | M | A, B, D, E, J, K, N | 23, 28 | Marshals Caution boards Hazard marked on map |
| 24. | 8.55 |  | Finish before crossing road | L | A, B, D, E, J, K, N | 23, 28 | n/a |

Green Belt Relay - Risk Assessment

Leg 20  -     West Hanger to Ripley       6 miles

| Course Identification | Green Belt Relay Stage 20 |  |  | A | B | C | D |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Whole event codes (1-8),(17, 29 & 31): 3, 4, 5, 7, 8, 17, 29, 31 |  |  |  | H/M/L | A to H | 9 to 30 only | R=Right, L=Left, SO=Straight On, FP=Footpath, FB=Footbridge |
| ID No | Miles from start | Details of hazard |  | Risk Rating level H/M/L | Persons at risk from hazard |  | Additional measures to reduce risk to LOW, with name of person or official function who will reduce the risk to low (if applicable) |
|  |  | Symbol | Desc |  |  |  |  |
| 1. | 0.0 – 0.1 |  | Start on footpath, merges with quiet road | L | A, B. C, D, E, I, J, K | 11 | n/a |
| 2. | 0.1 – 2.6 |  | Road – Coombe Lane, Staple Lane. | L | A, D, E, J, K | 23 | n/a |
| 3. | 2.6 |  | Road crossing - Cross A246 to West Horsley at roundabout using traffic islands | H | A, B, C, D, E, J, K | 11, 23 | Marshals Caution boards. Hazard marked on map. |
| 4. | 2.6 – 3.0 |  | Pavement through West Horsley | L | A, D, E, I, J, K | 23 | n/a |
| 5. | 3.0 – 3.2 |  | Cross road (“The Street”) and turn into cul-de-sac Silkmore Lane | L | A, D, E, I, J, K | 23 | n/a |
| 6. | 3.2 – 4 |  | Footpath | L | A, D, E, I, J, K | 23 | n/a |
| 7. | 4 |  | Turn right into Ripley Road from footpath | M | A, D, E, J, K | 11, 23 | Marshals Caution boards. Hazard marked on map. |
| 8. | 4.0 – 5 |  | Follow Ripley Road to finish | L/M | A, C, D, E, J, K | 11, 23 | Marshals Caution boards Hazard marked on map |
| 15. | 5 |  | crossroads - SO over staggered crossroads – Ripley Lane becomes Rose Lane | L | A, D, E, J, K | 11, 23 | n/a |
| 18. | 5.6 |  | Bridge over A3 - Rose Lane on bridge over A3. Narrow pavements on both sides of road | L | A, D, E, I, J, K | 23 | n/a |
| 19. | 6 |  | Social Club - Ripley British Legion Club. Marshals at finish. | L | A, B, C, D, E, I, J, K | 11, 23 | n/a |

Green Belt Relay - Risk Assessment

Leg 21  -    Ripley    to    Walton Bridge        8.4  miles

| Course Identification | Green Belt Relay Stage 21 |  |  | A | B | C | D |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Whole event codes (1-8),(17, 29 & 31): 3, 4, 5, 7, 8, 17, 29, 31 |  |  |  | H/M/L | A to H | 9 to 30 only | R=Right, L=Left, SO=Straight On, FP=Footpath, FB=Footbridge |
| ID No | Miles from start | Details of hazard |  | Risk Rating level H/M/L | Persons at risk from hazard |  | Additional measures to reduce risk to LOW, with name of person or official function who will reduce the risk to low (if applicable) |
|  |  | Symbol | Desc |  |  |  |  |
| 1. | 0.0 – 0.2 |  | Path - Start on Ripley Green, just behind Ripley Guitars. SO on FP across green and past playground to RHS | L | A, B, C, D, E, I, J, K | 11, 28 | n/a |
| 2. | 0.2 – 0.4 |  | Road - SO on road past Dunsborough Farm to LHS | L | A, D, E, I, J, K | 23, 28 | n/a |
| 3. | 0.4 |  | Road turns Left - Follow road L and after 150m SO onto FP | L | A, D, E, I, J, K | 23, 28 | n/a |
| 4. | 0.4 – 0.6 |  | Path - Path to Walsham Lock | L | A, I, J, K | 23, 28 | n/a |
| 5. | 0.6 |  | Lock - SO across FB weir at Walsham Lock then R along towpath past lock | L | A, I, J, K | 23, 28 | n/a |
| 6. | 0.6 – 1.5 |  | Canal Towpath - River Wey Navigation Towpath | L | A, I, J, K |  | n/a |
| 7. | 1.5 |  | Road crossing - Towpath crosses road at Pyrford Lock | M | A, B, C, D, E, I, J, K | 11 | Marshals Caution Boards Hazard marked on map |
| 8. | 1.5 – 3.3 |  | Canal Towpath - River Wey Navigation Towpath | L | A, I, J, K |  | n/a |
| 9. | 3.3 |  | Road crossing - Towpath crosses Old Parvis Road | L | A, D, E, I, J, K | 23, 28 | n/a |
| 10. | 3.3 – 4.5 |  | Canal towpath - River Wey Navigation Towpath | L | A, I, J, K | 23 | n/a |
| 11. | 4.5 |  | Road crossing - SO across A318 (Byfleet Road) at New Haw Lock and back onto towpath. | H | A, B, C, D, E, I, J, K | 11, 23 | At least 2 marshals Caution boards Hazard marked on map |
| 12. | 4.5 – 5.5 |  | Canal towpath - River Wey Navigation Towpath | L | A, I, J, K | 23 | n/a |
| 13. | 5.5 – 5.8 |  | Bridge / towpath - Cross over Black Boy Bridge and back down onto and along towpath on opposite side of river. | L | A, D, E, I, J, K | 23, 28 | n/a |
| 14. | 5.8 |  | Road crossing - At Weybridge Lock, towpath comes up to road (Addlestone Road). Cross straight over, turn R for 25m then L down across FB & back onto towpath | H | A, B, C, D, E, I, J, K | 11, 23 | Marshals Caution boards Hazard marked on map |
| 15. | 5.8 – 6.5 |  | Canal towpath - River Wey Navigation Towpath | L | A, I, J, K | 23 | n/a |
| 16. | 6.5 |  | Footbridge - At Thames Lock turn R over FB. Narrow steep footbridge. | L | A, I, J, K | 23 | n/a |
|  | 6.5 – 6.6 |  | Path - SO along FP, at junction veer R | L | A, I, J, K | 23, 28 | n/a |
|  | 6.6 – 6.65 |  | Road - L onto road. At Y-junction veer R and over bridge. - Very quiet private road. | L | A, D, E, I, J, K | 23 | n/a |
| 17. | 6.65 – 6.75 |  | Path - Immediately over bridge, turn L onto Church Walk – Footpath | L | A, I, J, K | 11, 23 | n/a |
| 18. | 6.75 |  | Pub car park - Old Crown car park. | L | A, D, E, I, J, K | 23 | n/a |
| 19. | 6.75 – 6.9 |  | Pavement - Turn L on pavement along Thames Street | L | A, D, E, I, J, K | 23 | n/a |
| 20. | 6.9 |  | Carpark - Veer L through riverside car park. | L | A, D, E, I, J, K | 23 | n/a |
| 21. | 6.9 – 8.4 |  | Towpath - SO on towpath along Desborough Cut. | L | A, H, I, J, K | 23 | n/a |
| 22. | 8.4 |  | Towpath - Finish on towpath at Walton Bridge. | L | A, B, C, I, J, K | 11 | n/a |

Green Belt Relay - Risk Assessment

Leg 22  -    Walton Bridge    to    Bushy Park Sports Club  8 miles

| Course Id | Green Belt Relay Stage 22 |  |  | A | B | C | D |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Whole event codes (1-8),(17, 29 & 31): 3, 4, 5, 7, 8, 17, 29, 31 |  |  |  | H/M/L | A to H | 9 to 30 only | R=Right, L=Left, SO=Straight On, FP=Footpath, FB=Footbridge |
| ID No | Miles from start | Details of hazard |  | Risk Rating level H/M/L | Persons at risk from hazard |  | Additional measures to reduce risk to LOW, with name of person or official function who will reduce the risk to low (if applicable) |
|  |  | Symbol | Desc |  |  |  |  |
| 1. | 0.0 |  | Towpath - Start on Thames Path at Walton Bridge | L | A, B, C, D, E, I, J, K | n/a | n/a |
| 2. | 4.65 – 4.75 |  | Road - SO along road. Stay on LHS - Riverbank | L | A, D, E, I, J, K | n/a | n/a |
| 3. | 4.75 – 4.85 |  | Pavement - Turn L on pavement over Hampton Court Bridge | L | A, I, J, K | n/a | n/a |
| 4. | 5 |  | Road crossing - Use zebra crossing to cross Hampton Court Road. Busy road, but fairly slow traffic, good visibility and zebra crossing | M | A, B, C, D, E, I, J, K | 11 | Marshals Caution boards Hazard marked on map |
| 6. | 5.1 |  | Cross road at Lion Gate and continue on pavement. Slow traffic but cars turning in | M | A, D, E, I, J, K | 11 | Marshals Caution boards Hazard marked on map |
| 8. | 6.3 |  | Turn left into Church Grove | L | A, B, C, D, E, I, J, K | n/a | n/a |
| 9. | 7.6 |  | Cross road at gate and continue on pavement. Slow traffic but cars turning in | M | A, B, C, I, J, K | 11 | Marshals Caution boards Hazard marked on map |
| 10. | 7.9 |  | L into Bullard Rd, cross roundabout Very slow traffic | L | A, B, C, I, J, K | n/a | n/a |
| 11. | 8 – 8.2 |  | Run on pavement into grounds of Sports Centre and finish on sports fields. | L | A, B, C, I, J, K | n/a | n/a |

Green Belt Relay - Notes for guidance for the completion of this Risk Assessment:

HAZARD 		means the potential to cause harm

RISK 			means the degree of likelihood that a hazard will cause harm

PERSONS AT RISK	who may be affected by a risk

RISK 			therefore reflects both the likelihood that harm will occur and its severity

RISK ASSESSMENT 	is controlling the level of risk; it might be summarised as follows:

LOOK…EVALUATE…ACT…REVIEW

Generic Risk Assessment Codes

| COLUMN A Hazard Risk rating level H = HIGH M = MEDIUM L = LOW | COLUMN C Measures to reduce risk to low. Items 1-8, 29 & 31 to be included in ALL events, and the whole course - Code of Practice advanced signing on approach to course - Code of Practice safety signs or marshals every time there is danger - Safety briefing to all competitors (Team captains at a meeting 3 weeks before the relay, to feed back to their competitors before the event and Starters of each leg to brief competitors before the start of each leg) - Safety briefing to all marshals - Compliance with traffic law by Competitors/Officials/Marshals - All marshals to wear Hi-Vis clothing - Advance liaison with interested parties - Event vehicles to be identified |  |
| --- | --- | --- |
| COLUMN B PERSONS AT RISK - COMPETITORS - SPECTATORS - ORGANISERS / MARSHALS - ONCOMING TRAFFIC - PASSING TRAFFIC - CROSSING FROM RIGHT - CROSSING FROM LEFT - PEOPLE CARRYING BOATS - PUBLIC - PEDESTRIANS inc. DOGS - CYCLISTS - CONSTRUCTION WORKERS | - Road closures - Additional road signs - Junctions to be marshalled by: __at least 2 marshals - Traffic signals to be manually controlled - Traffic signals to be marshalled - Motorcycle Police escort - Motorcycle safety marshal - Pedestrian crossing to be marshalled - Marshals to have method of communication - Officials to be identified - Not open during event - Establish time of other events and review - Protective barriers in front of spectators - Physical protection (e.g. straw bales) - Signposted for competitors - Protected for traffic coning - Protected access/egress for emergency vehicles - Uniformed Police/Traffic Warden - Marshal with authority to place mandatory road closed sign: |  |
| M . LIVESTOCK | - Specify: | Direction to be marked with sawdust |
| N. HORSE & RIDER | - Specify: | Maps to be marked with hazards and have contact telephone number |
| P. GOLFERS | - Specify: | Competitors to be paced slowly for first part of leg |
| R. Market Traders | - Specify: | Competitors told to take care on paths / roads next to rivers |